## Main Sheet
SL No | Site ID | Site Name | Project Name | TCL Standard TAT (Days) | Site Assigned Date | Permission receive date | Activity Name | Completed Date | PNS TAT (in Days) | Site Complete Status | Remark’s. | Next Planning Date | FO Team TAT (in Days) | WO released or Not
1 | BIHPAT0269 | Fatuwah-01 | RF Capacity augmentation 65 BS 100 to 45 | 5 | 2025-07-07 | 2025-08-07 | BTS dismantling | 2025-10-07 | 2 | Fully Completed |  | NA |  | Received
2 | BIHPAT0282 | Maner-01 | RF Capacity augmentation 65 BS 100 to 45 | 5 | 2025-07-07 | 2025-09-07 | BTS dismantling | 2025-11-07 | 2 | Fully Completed |  | NA |  | Received
3 | WEBQKL0070 | Kaji Para (kalikapur) | Low Potential Sector dismantling – 349 Sectors | 5 | 16-07-2025 | 2025-09-07 | BTS dismantling | 2025-11-07 | 2 | Fully Completed |  | NA |  | Received
4 | IN-1087991 | Salt Lake BG Block | Emergency Relocation | 5 | 2025-10-07 | 2025-11-07 | BTS dismantling | 2025-12-07 | 1 | Fully Completed |  | NA |  | Received
5 | JHAQJS0017 | BISTAMPUR | TTL Roll back | 5 | 2025-07-07 | 2025-11-07 | BTS dismantling | 2025-12-07 | 1 | Fully Completed |  | NA |  | Received
6 | IN-2037549 | Karnamstret_Odf | L1-L2 improvement FY24 Ph-2, 80 sites | 3 | 14-06-2025 | 17-06-2025 | BTS survey | 2025-12-07 | 24 | Fully Completed |  | NA |  | Received
7 | TROR0035 | Jeypur | L1-L2 improvement FY24 Ph-2, 80 sites | 3 | 14-06-2025 | 17-06-2025 | UBR BH survey | 2025-12-07 | 24 | Fully Completed |  | NA |  | Received
8 | JHAQJS0134 | RADWIN_West Chaibasa-01 | TTL Roll back | 5 | 2025-07-07 | 2025-11-07 | P2P link dismantling | 2025-12-07 | 1 | Fully Completed |  | NA |  | Received
9 | INBR007112 | R.P.S COLONY | L1-L2 improvement FY24 Ph-2, 80 sites | 5 | 2025-10-07 | 2025-11-07 | BTS installation | 2025-12-07 | 1 | Fully Completed |  | NA |  | Received
10 | WEBNOR0611 | Khardah | ORCO POC | 5 | 2025-07-07 | 2025-12-07 | BTS installation | 14-07-2025 | 2 | Fully Completed |  | NA |  | Received
11 | JHADHA0048 | Mugma | Low Potential Sector dismantling – 349 Sectors | 5 | 16-07-2025 | 16-07-2025 | BTS dismantling | 17-07-2025 | 1 | Fully Completed |  | NA |  | Received
12 | JHADHA0431 | Govindpur (Dhanbad) | Low Potential Sector dismantling – 349 Sectors | 5 | 16-07-2025 | 16-07-2025 | BTS dismantling | 17-07-2025 | 1 | Fully Completed |  | NA |  | Received
13 | WEBNOR0731 | Kaliaganj | Low Potential Sector dismantling – 349 Sectors | 5 | 2025-03-07 | 15-07-2025 | BTS dismantling | 17-07-2025 | 2 | Fully Completed |  | NA |  | Received
14 | IN-1086788 | RANINAGAR | L1-L2 Improvement- 40 Sites | 3 | 18-07-2025 | 20-07-2025 | BTS Survey | 21-06-2025 | 1 | Fully Completed |  | NA |  | Received
15 | WEBNOR0692 | Barasat High Court | Low Potential Sector dismantling – 349 Sectors | 5 | 21-07-2025 | 22-07-2025 | BTS dismantling | 25-07-2025 | 3 | Fully Completed |  | NA |  | Received
16 | WEBBIR0038 | BOLPUR_004 | Low Potential Sector dismantling – 349 Sectors | 5 | 21-07-2025 | 22-07-2025 | BTS dismantling | 25-07-2025 | 3 | Fully Completed |  | NA |  | Received
17 | ORIKAL0213 | Dharamgarh_Block Chowk | Low Potential BS dismantling 50 BS | 5 | 21-07-2025 | 13-08-2025 | BTS dismantling | 16-08-2025 | 3 | Fully Completed |  | NA |  | Received
18 | 091HOOG623036115077 | Indian Bank | BS Augment: UBR Backhaul to Direct FY24 | 5 | 16-06-2025 | 18-08-2025 | Customer PMP Installation | 22-08-2025 | 3 | Fully Completed |  | NA |  | Received
19 | 091DANK0300A0113758 | MORE RETAIL PRIVATE LIMITED | BS Augment: UBR Backhaul to Direct FY24 | 5 | 16-06-2025 | 25-08-2025 | Customer PMP Installation | 25-08-2025 | 1 | Fully Completed | Installation completed but device replacement required // Please provide device | NA |  | Received
20 | 091KOLK623037957470 | APOLLO HEALTHCO LIMITED | BS Augment: UBR Backhaul to Direct FY24 | 5 | 16-06-2025 | 2025-09-08 | Customer PMP Installation | 14-08-2025 | 4 | Fully Completed |  | NA |  | Received
21 | 091KOLK030036733975 | Ingram Micro India Private Limited | BS Augment: UBR Backhaul to Direct FY24 | 5 | 16-06-2025 | 24-06-2025 | Customer P2P Installation | 2025-01-09 | 33 | Fully Completed | Device replacement is required at both ends, but the planning is on hold due to waterlogging issues. | WIP |  | Received
22 | INBR005143 | JAIL CHOWK | Non Performing BS Optimization FY 24 | 3 | 21-07-2025 | 21-07-2025 | Converter installation + VIVA BH Survey | 22-07-2025 | 1 | Fully Completed |  | NA |  | Received
23 | BIHSUP0381 | Supaul-02 | BS Augment: UBR Backhaul to Direct FY 24 | 3 | 21-07-2025 | 22-07-2025 | Converter installation + VIVA BH Survey | 23-07-2025 | 1 | Fully Completed |  | NA |  | Received
24 | 091HOOG623013586123 | IDBI BANK LTD | ORCO POC | 3 | 28-07-2025 | 2025-01-08 | Survey Customer | 2025-01-08 | 1 | Fully Completed |  | NA |  | Received
25 | 091HOOG030037240796 | Jubilant Foodworks Limited | ORCO POC | 3 | 28-07-2025 | 2025-01-08 | Survey Customer | 2025-01-08 | 1 | Fully Completed |  | NA |  | Received
26 | IN-1064376 | EBANBANGAON011 | Non Performing BS Optimization Ph-10A |  | 2025-02-08 | 2025-03-08 | Migration | 2025-03-08 | 1 | Fully Completed |  | NA |  | Received
27 | JHARAN0235 | Pisca more | UBR BH Augmentation FY25_26 | 5 | 2025-02-08 | 2025-03-08 | UBR Installation | 2025-04-08 | 1 | Fully Completed | Installation completed but UBR BH alignment pending duo to Honey Bee issue, AT completed but device foulty, Required BW is not received | NA |  | Received
28 | 091KOLK030035997332 | Jubilant Foodworks Limited | CX4 to Conventional BH FY 25 | 3 | 2025-04-08 | 2025-04-08 | Cx2 Survey | 17-12-2025 | 1 | Fully Completed |  | NA |  | Received
29 | 7518 | SITAMARHI | CX4 to Conventional BH FY 25 | 5 | 27-07-2025 | 2025-04-08 | Converter installation + VIVA BH Survey | 2025-05-08 | 1 | Fully Completed |  | NA |  | Received
30 | JHARAN0553 | UW_BIHAR_1690_Hatma_Ranchi | RF platform migration: Cambium 100 to 45 | 5 | 28-07-2025 | 2025-03-08 | BTS installation | 2025-05-08 | 2 | Fully Completed |  | NA |  | Received
31 | JHADHA0287 | Dhanbad-10 | RF platform migration: Cambium 100 to 45 | 5 | 28-07-2025 | 2025-03-08 | BTS installation | 2025-05-08 | 2 | Fully Completed |  | NA |  | Received
32 | BIHPAT1066 | UW_BIHAR_1581_ASHOKRAJ PATH | UBR BH Augmentation FY25_26 | 5 | 28-08-2025 | 2025-05-08 | UBR Installation | 2025-07-08 | 2 | Fully Completed | Installation completed //alingment pending | NA |  | Received
33 | IN-2037549 | Karnamstret_Odf | L1-L2 improvement FY24 Ph-2, 80 sites | 5 | 30-072025 |  | BTS installation |  |  | Dropped | The site has been dropped. | WIP |  | Received
34 | IN-1038105 | HEMSHREE APPARTMENT | L1-L2 improvement FY24 Ph-2, 80 sites | 5 | 30-072025 | 14-08-2025 | BTS installation | 28-08-2025 | 13 | Fully Completed | The FE was busy with the Dankuni North customer, and on Saturday, DT activity (Ramrajatala and Jagacha UBR alignment activities) & Sunday ticket was not available. | NA |  | Received
35 | BIHEAS0117 | Sugauli_Motihari | TTL rollback project | 5 | 2025-07-08 | 2025-12-08 | BTS dismantling | 2025-12-08 | 1 | Fully Completed |  | NA |  | Received
36 | IN-1063220 | ENAWNAWDIP031 | T34P-Switch replacement FY25 | 5 | 2025-12-08 | 19-08-2025 | Switch Installation | 19-08-2025 | 1 | Fully Completed |  | NA |  | Received
37 | OR/CU/VF/0051 | Ranihat | T34P-Switch replacement FY25 | 5 | 15-08-2025 | 25-08-2025 | Switch Installation | 25-08-2025 | 1 | Fully Completed |  | NA |  | Received
38 | BIHPAT1042 | Exhibition Road | RF Capacity augmentation 65 BS 100 to 45 | 5 | 27-08-2025 | 29-08-2025 | BTS installation | 30-08-2025 | 2 | Fully Completed |  | NA |  | Received
39 | BIHQGA0116 | New Dhiliya | CX4 to Conventional BH FY 25 | 5 | 29-08-2025 | 30-08-2025 | Converter installation + VIVA BH Survey | 2025-01-09 | 1 | Fully Completed |  | NA |  | Received
40 | ID-1000888 | Sasaram | CX4 to Conventional BH FY 25 | 5 | 29-08-2025 | 30-08-2025 | Converter installation + VIVA BH Survey | 2025-01-09 | 1 | Fully Completed |  | NA |  | Received
41 | 091DHAN623014602843 | STATE BANK OF INDIA | RF platform migration: Cambium 100 to 45 | 5 | 2025-04-09 | 2025-05-09 | Customer Installation | 2025-05-09 | 1 | Fully Completed |  | NA |  | Received
42 | ORIKHU0254 | BBSR_BIGBAZAR | UBR BH Augmentation FY25_26 | 5 | 2025-12-09 | 14-05-2025 | UBR Installation | 14-05-2025 | 1 | Fully Completed |  | NA |  | Received
43 | 091SIWA623032577554 | ICICI Bank Limited | Platform Migration-Ph4 PTP To PMP | 5 | 22-09-2025 | 14-10-2025 | Customer Dismantle | 16-10-2025 | 2 | Fully Completed | Delay due to permission issue. | NA |  | Received
44 | 091PATN623035909459 | Franklin Templeton Asset Management (India) Private Limited | Platform Migration-Ph4 PTP To PMP | 5 | 22-09-2025 | 24-09-2025 | Customer Dismantle | 26-09-2025 | 2 | Fully Completed | Delay due to permission issue. | NA |  | Received
45 | 091CHHA623017545879 | ICICI Bank Limited | Platform Migration-Ph4 PTP To PMP | 5 | 22-09-2025 | 24-09-2025 | Customer Dismantle | 25-09-2025 | 4 | Fully Completed | Delay due to permission issue. | NA |  | Received
46 | 091PATN623036070071 | BANK OF BARODA | Platform Migration-Ph4 PTP To PMP | 5 | 22-09-2025 | 24-09-2025 | Customer Dismantle | 26-09-2025 | 2 | Fully Completed | Delay due to permission issue. | NA |  | Received
47 | 091JAMT623036114082 | Indian Bank | ZTS Relocation FY 24 | 5 | 2025-10-10 | 15-10-2025 | Survey + Installation | 16-10-2025 | 1 | Fully Completed |  | NA |  | Received
48 | 091KOLK623035555916 | PUNJAB NATIONAL BANK | ZTS Relocation FY 24 | 5 | 2025-11-09 | 2025-11-11 | PMP Survey | 2025-11-11 | 1 | Fully Completed |  | NA |  | Received
49 | 091ARWA0300A0134863 | HDFC Bank Limited | ZTS Relocation FY 24 | 5 | 2025-10-10 | 20-10-2025 | Survey + Installation | 22-10-2025 | 2 | Fully Completed | LC details required | NA |  | Received
50 | 091DALT6230A0060187 | Bharti AXA Life Insurance Company Limited | PTP to PMP Conversion 5 | 3 | 2025-10-10 |  | Customer Survey |  |  | Dropped |  | NA |  | Received
51 | 091HAZA6230A0060179 | Bharti AXA Life Insurance Company Limited | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 27-11-2025 | Customer Survey | 29-11-2025 | 2 | Fully Completed | LC details required | NA |  | Received
52 | 091HAZA6230A0060179 | Bharti AXA Life Insurance Company Limited | PTP to PMP Conversion 5 | 5 | 2026-01-08 | 2026-01-10 | Survey Task Closed | 2026-01-10 | 2 | Fully Completed | LC details required | NA |  | Received
53 | 091HAZA6230A0060179 | Bharti AXA Life Insurance Company Limited | PTP to PMP Conversion 5 | 5 | 2025-10-12 | 15-12-2025 | Customer Installation | 17-12-2025 | 2 | Fully Completed | LC details required | NA |  | Received
54 | 091HAZA6230A0060179 | Bharti AXA Life Insurance Company Limited | PTP to PMP Conversion 5 | 5 | 24-12-2025 | 24-12-2025 | Customer Migration | 24-12-2025 | 1 | Fully Completed | LC details required | NA |  | received
55 | 091GAYA623032344230 | IndusInd Bank Limited | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 2025-11-11 | Customer Survey | 2025-12-11 | 1 | Fully Completed | LC details required | NA |  | Received
56 | 091SITA623037548460 | TCS (PASSPORT SEVA PROJECT) | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 24-11-2025 | Customer Survey | 26-11-2025 | 1 | Fully Completed | LC details required | NA |  | Received
57 | 091BEGU623035559423 | HINDUSTAN PETROLEUM CORPORATION LTD | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 2025-05-11 | Customer Survey | 2025-07-11 | 2 | Fully Completed | LC details required | NA |  | Received
58 | 091BHAG623035736754 | STATE BANK OF INDIA | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 2025-11-11 | Customer Survey | 13-11-2025 | 2 | Migration WIP | Permission require | NA |  | Received
59 | 091BHAG623032465375 | CARE HEALTH INSURANCE LIMITED | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 2025-11-11 | Customer Survey | 13-11-2025 | 2 | Fully Completed | LC details required | NA |  | Received
60 | 091PATN623035817290 | IDFC FIRST BANK LIMITED | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 14-10-2025 | Customer Survey | 15-10-2025 | 1 | Fully Completed | The site was completed during direct visit. | NA |  | Received
61 | 091RANC623035558828 | HINDUSTAN PETROLEUM CORPORATION LTD | PTP to PMP Conversion 5 | 3 | 2025-10-10 |  | Customer Survey |  |  | Dropped |  | NA |  | Received
62 | 091MUSH6230A0041925 | Axis Bank Limited | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 16-11-2025 | Customer Survey | 17-11-2025 | 2 | Installatio WIP | Device required | NA |  | Received
63 | 091PATN030036880209 | L'Oreal C/O Singapore Telecommunications Limited | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 14-10-2025 | Customer Survey | 15-10-2025 | 1 | Fully Completed | The site was completed during direct visit. | NA |  | Received
64 | 091AURA623037554260 | TCS (PASSPORT SEVA PROJECT) | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 23-11-2025 | Customer Survey | 25-11-2025 | 2 | Fully Completed | LC details required | NA |  | Received
65 | 091PATN623037274769 | TATA Capital Limited | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 14-10-2025 | Customer Survey | 14-10-2025 | 1 | Fully Completed | The site was completed during direct visit. | NA |  | Received
66 | 091PATN623034402094 | BANK OF BARODA | PTP to PMP Conversion 5 | 3 | 2025-10-10 | 18-11-2025 | Customer Survey | 19-11-2025 | 1 | Installatio WIP | Device required | NA |  | Received
67 | WEBSOU0881 | Nurpur_001 | BH migration from TTSL to alternate FY25 | 5 | 14-10-2025 | 20/10/2025 | BS Dismantle | 22/10/2025 | 2 | Fully Completed |  | NA |  | Received
68 | WEBWES0961 | Haldia_004 | BH migration from TTSL to alternate FY25 | 5 | 14-10-2025 | 20/10/2025 | BS Dismantle | 21/10/2025 | 1 | Fully Completed |  | NA |  | Received
69 | WEBSOU0826 to WEBHOW0256 | Ranihat Amta to Rajdanga Andul | BS Augment: UBR Backhaul to Direct FY24 | 5 | 28-10-2025 | 2025-04-11 | UBR Dismantle | 2025-05-11 | 1 | Fully Completed |  | NA |  | Received
70 | WEBNOR0611 | Khardah | ORCO POC | 5 | 2025-01-11 | 2025-03-11 | BS Dismantle | 2025-03-11 | 1 | Fully Completed | Taks WIP | NA |  | Received
71 | JHAHAZ0165 | Hazaribagh Nawabganj | Capacity Augmentation - UBR-Q2 FY 24 | 5 | 13-11-2025 | 27-11-2025 | BS Dismantle | 29-11-2025 | 2 | Fully Completed |  | NA |  | Received
72 | BIHSUP0381 | Supaul-02 | Capacity Augmentation - UBR-Q2 FY 24 | 5 | 13-11-2025 | 26-11-2025 | BS Dismantle | 29-11-2025 | 3 | Fully Completed |  | NA |  | Received
73 | WEBBAN0012 | Bankura_002 | BS Augment: UBR Backhaul to Direct FY24 | 5 | 13-11-2025 | 14-11-2025 | BS Dismantle | 14-11-2025 | 1 | Fully Completed |  | NA |  | Received
74 | IN-1022958 | BISHNUPUR | BS Augment: UBR Backhaul to Direct FY24 | 5 | 13-11-2025 | 19-12-2025 | BS Dismantle | 19-12-2025 | 1 | Fully Completed |  | NA |  | Received
75 | 091DHAN6230A0006492 | Trent Limited | PTP to PMP Conversion 5 | 3 | 13-10-2025 | 14-11-2025 | Customer Survey | 14-11-2025 | 2 | Installatio WIP | Device required | NA |  | Received
76 | 091DHAN623035499522 | FIS Payment Solutions & Services India Private Limited | PTP to PMP Conversion 5 | 3 | 13-10-2025 | 14-11-2025 | Customer Survey | 14-11-2025 | 2 | Fully Completed |  | NA |  | Received
77 | BIHVAI0384 | Hazipur | Emergency Relocation | 5 | 14-11-2025 | 16-11-2025 | BTS installation | 12/06-2025 | 16 | Fully Completed | Damage device received, CMM received 1st-dec-2025 | NA |  | Received
78 | 091JEHA623005989241 | Axis Bank Limited | PTP to PMP Conversion 5 | 3 | 2025-03-12 | 2025-11-12 | Customer Survey | 2025-12-12 | 1 | Installatio WIP |  | NA |  | Received
79 | 091HAZA623036194122 | Bank of India | PTP to PMP Conversion 5 | 3 | 2025-03-12 |  | Customer Survey |  |  | Pending/YTS | LC required | NA |  | Received
80 | 091JAMS623032961482 | Tata Motors Limited | PTP to PMP Conversion 5 | 3 | 2025-03-12 | 2025-11-12 | Customer Survey | 2025-12-12 | 1 | Fully Completed | LC required | NA |  | Received
81 | 091PATN623014935147 | Amway India Enterprises Private Limited | PTP to PMP Conversion 5 | 3 | 2025-03-12 | 2025-04-12 | Customer Survey | 2025-05-12 | 1 | Installatio WIP | Device required | NA |  | Received
82 | 091SAHA623033872882 | Maruti Suzuki India Ltd | PTP to PMP Conversion 5 | 3 | 2025-03-12 |  | Customer Survey |  |  | Pending/YTS | LC required | NA |  | Received
83 | OR/JA/AI/0279 | Jagatsinghpur | CX4 to Conventional BH FY 26 | 3 | 2025-08-12 | 2025-09-12 | BTS Survey | 2025-12-12 | 3 | Fully Completed |  | NA |  | Received
84 | 091JAGA623037541548 | TCS PASSPORT SEVA PROJECT | CX4 to Conventional BH FY 26 | 3 | 2025-08-12 | 2025-09-12 | Customer Survey | 2025-12-12 | 3 | Fully Completed |  | NA |  | Received
85 | 091CUTT623034701768 | UNION BANK OF INDIA- erstwhile CB | CX4 to Conventional BH FY 26 | 3 | 2025-08-12 | 2025-09-12 | Customer Survey | 2025-12-12 | 3 | Fully Completed |  | NA |  | Received
86 | 091JAGA6230A0029431 | DCB Bank Limited | CX4 to Conventional BH FY 26 | 3 | 2025-08-12 | 2025-09-12 | Customer Survey | 2025-12-12 | 3 | Fully Completed |  | NA |  | Received
87 | VFBRMDH0867 | Ward No-7 By Pass Road | L1-L2 Improvement- 40 Sites | 3 | 2025-11-12 |  | RAP Site Installation Activity |  |  | Dropped |  | NA |  | Received
88 | ORIBOL0603 | BOLANGIR_02_GSM(Rajendra Para) | L1-L2 Improvement- 40 Sites | 3 | 2025-11-12 | 24-12-2025 | RAP Site Installation Activity | 24-12-2025 | 1 | RFI Pending |  | NA |  | Received
89 | BIHMAD0198 | Madhubani O1 | L1-L2 Improvement- 40 Sites | 3 | 2025-12-11 | 23-12-2025 | RAP Site Installation Activity | 23-12-2025 | 1 | Fully Completed |  | NA |  | Received
90 | BIHJAM0890 | UW_BIHAR_1502_Maharajganj-Kalyanpur | L1-L2 Improvement- 40 Sites | 3 | 2025-11-12 | 23-12-2025 | RAP Site Installation Activity | 23-12-2025 | 1 | Fully Completed |  | NA |  | Received
91 | 091KOLK030035997332 | Jubilant Foodworks Limited | CX4 to Conventional BH FY 25 | 5 | 16-12-2025 | 18-12-2025 | Cx2 Installation | 18-12-2025 | 1 | Fully Completed |  | NA |  | Received
92 | WEBEAS1376 | Ramnagar | BH Augmentation - FY25_105 | 3 | 18-12-2025 | 19-12-2025 | UBR BH alignment | 19-12-2025 | 1 | Fully Completed |  | NA |  | Received
93 | INBR000795 | JAGJIWAN PATH | L1-L2 Improvement- 40 Sites | 3 | 23-12-2025 | 23-12-2025 | RAP Site Installation Activity | 23-12-2025 | 1 | Fully Completed |  | NA |  | Received
94 | BIHMAD0198 | Madhubani O1 | L1-L2 Improvement- 40 Sites | 3 | 2025-11-12 | 26-12-2025 | Switch Installation | 26-12-2025 | 1 | Fully Completed |  | NA |  | Received
95 | BIHJAM0890 | UW_BIHAR_1502_Maharajganj-Kalyanpur | L1-L2 Improvement- 40 Sites | 3 | 2025-11-12 | 29-12-2025 | Switch Installation | 29-12-2025 | 1 | Fully Completed |  | NA |  | Received
96 | 091JAGA6230A0029431 | DCB Bank Limited | CX4 to Conventional BH FY 26 | 3 | 2025-08-12 | 13-12-2025 | Customer P2P Survey With device | 15-12-2025 | 2 | Fully Completed |  | NA |  | Received
97 | JHARAN0553 | UW_BIHAR_1690_Hatma_Ranchi | UW_BIHAR_1690_Hatma_Ranchi | 5 | 2026-02-01 | 2026-04-01 | Sector Dismantle | 2026-01-07 | 3 | Fully Completed |  | NA |  | Received
98 | 091KOLK030035997332 | Jubilant Foodworks Limited | CX4 to Conventional BH FY 25 | 5 | 2026-07-01 | 2026-08-01 | Additional Visit | 2026-01-07 | 1 | Fully Completed |  | NA |  | Received
99 | 091DALK623034374076 | UNION BANK OF INDIA- erstwhile CB | CX4 to conventional FY26 | 5 | 2026-07-01 | 2026-08-01 | Cx2 Installation | 2026-08-01 | 1 | Fully Completed |  | NA |  | Received
100 | BIHDAR0781 | RAHAMGANJ | RF platform migration: Cambium 100 to 45 | 5 | 14-01-2026 | 16-01-2026 | Sector Dismantle | 19-01-2026 | 3 | Fully Completed | PO Balance Issue | NA |  | Received
101 | BIHVAI1078 | E_BIH_1783-HAZIPUR-10 | Emergency Relocation | 5 | 20-01-2026 | 21-01-2026 | BTS Dismantle | 21-01-2026 | 1 | Fully Completed |  | NA |  | Received
102 | BIHVAI1078 to BIHVAI0384 | E_BIH_1783-HAZIPUR-10 to Hazipur | Emergency Relocation | 5 | 21-01-2026 | 21-01-2026 | UBR Dismantle | 22-01-2026 | 2 | Fully Completed |  | NA |  | Received
103 | WEBHOW0260 | Liluah Station South | RF Capacity augmentation 65 BS 100 to 45 | 5 | 22-01-2026 | 25/3/2026 | BTS Dismantle | 28/3/2026 | 3 | Fully Completed |  | NA |  | Received
104 | WEBHOO0191 | Baidyabati | RF Capacity augmentation 65 BS 100 to 45 | 5 | 22-01-2026 | 25/3/2026 | BTS Dismantle | 27/3/2026 | 2 | Fully Completed |  | NA |  | Received
105 | 091ASAN623007844047 | HDFC Securities Limited | Multicast customer migration from PMP to | 5 | 22-01-2026 | 2026-02-02 | Customer Installation | 2026-04-02 | 2 | Fully Completed |  | NA |  | Received
106 | 091KOLK623005767629 | Tata Motors Finance Solution Limited | Multicast customer migration from PMP to |  | 22-01-2026 | 2026-02-02 | Customer Installation | 2026-03-02 | 1 | Migration WIP |  | NA |  | Received
107 | 3331253686 | HDFC Securities Limited | Multicast customer migration from PMP to |  | 22-01-2026 | 15-02-2026 | Customer Installation | 18-02-2026 | 3 | Fully Completed |  | NA |  | Received
108 | 091KOLK030035997332 | Jubilant Foodworks Limited | CX4 to Conventional BH FY 25 | 5 | 2026-07-01 | 29-01-2026 | Cx2 Dismantle | 30-01-2026 | 1 | Fully Completed |  | NA |  | Received
109 | BIHAUR0811 | Club Road | BH migration from TTSL to alternate FY25 | 3 | 27-01-2026 | 27-01-2026 | BTS Survey | 28-01-2026 | 1 | Fully Completed |  | NA |  | Received
110 | IN-1132627 | CHAKDAH-8 | BS Augment: UBR Backhaul to Direct FY24 BS | 5 | 28-01-2026 | 29-01-2026 | BTS Dismantle | 29-01-2026 | 1 | Fully Completed |  | NA |  | Received
111 | BIHSAH0324 | Saharsa-1 | Top 34 Accounts | 5 | 28-01-2026 | 30-01-2026 | BTS Dismantle | 2026-02-03 | 2 | Fully Completed |  | NA |  | Received
112 | 091JHAR6230A0007735 | IDFC FIRST BANK LIMITED | ZTS Relocation FY 24 | 5 | 28-01-2026 | 29-01-2026 | Customer Installation | 29-01-2026 | 1 | Fully Completed |  | NA |  | Received
113 | 091JHAR623030286908 | ICICI Prudential Life Insurance Company Limited | ZTS Relocation FY 24 | 5 | 28-01-2026 | 29-01-2026 | Customer Installation | 29-01-2026 | 1 | Fully Completed |  | NA |  | Received
114 | 091SAMB030038625732 | HDB Financial Services Limited | ZTS Relocation FY 24 | 5 | 28-01-2026 | 29-01-2026 | Customer Dismantle | 29-01-2026 | 1 | Fully Completed |  | NA |  | Received
115 | WEBHOW0262 to WEBHOW0276 | DSK Lane West to Metiaburutz | ZTS Relocation FY 24 | 5 | 2026-05-02 | 2026-02-06 | UBR BH Dismantle | 2026-02-09 | 3 | Fully Completed |  | NA |  | Received
116 | WEBNOR0639 | Kuntighat | Low Potential TTL BS Dismantling 67 | 5 | 2026-05-02 | 2026-02-06 | BTS Dismantle | 2026-02-07 | 1 | Fully Completed |  | NA |  | Received
117 | WEBNOR0639 to IN-1051501 | Kuntighat to Tribeni | Low Potential TTL BS Dismantling 67 | 5 | 2026-05-02 | 2026-02-06 | UBR BH Dismantle | 2026-02-07 | 1 | Fully Completed | IM Site access required | NA |  | Received
118 | JHADHA0287 | Dhanbad-10 | RF platform migration: Cambium 100 to 45 | 5 | 2026-09-02 | 2026-02-10 | BTS Dismantle | 2026-02-12 | 2 | Fully Completed |  | NA |  | Received
119 | WEBHOW0260 | Liluah Station South | CX4 to Conventional BH FY 25 | 3 | 20-02-2026 | 21-02-2026 | BTS Survey | 23-02-2026 | 2 | Fully Completed |  | NA |  | Received
120 | IN-1022944 | PALASHI | L1-L2 improvement FY24 Ph-2, 80 sites | 3 | 23-02-2026 | 23-02-2026 | BTS Survey | 24-02-2026 | 1 | Fully Completed |  | NA |  | Received
121 | BIHMAD0201 | Jhanjharpur_02 | L1-L2 improvement FY24 Ph-2, 80 sites | 3 | 25-02-2026 | 26-02-2026 | BTS Survey | 26-02-2026 | 1 | Fully Completed |  | NA |  | Received
122 | BIHMAD0201 | Jhanjharpur_02 | L1-L2 improvement FY24 Ph-2, 80 sites | 5 | 18-03-2026 | 18-03-2026 | Switch Installation | 18-03-2026 | 1 | Fully Completed |  | NA |  | Received
123 | WEBNOR0727 | Dalkhola_001 | ZTS Relocation FY 24 | 5 | 26-02-2026 | 28-02-2026 | BTS Dismantle | 2026-03-02 | 3 | Fully Completed |  | NA |  | Received
124 | 091DALK623034374076 | UNION BANK OF INDIA- erstwhile CB | ZTS Relocation FY 24 | 5 | 26-02-2026 | 28-02-2026 | Customer Dismante | 2026-03-02 | 3 | Fully Completed |  | NA |  | Received
125 | BIHAUR0811 | Club Road | BH migration from TTSL to alternate FY25 | 5 | 2026-03-02 | 2026-03-03 | UBR Installation | 2026-03-08 | 5 | Migration WIP | Device Issue, 2nd time device issue | NA |  | Received
126 | WEBHOW0260 to WEBHOW0261 | Liluah Station South to Panchanantala | CX4 to Conventional BH FY 25 | 5 | 2026-03-12 | 13-03-2026 | UBR Installation | 13-03-2026 | 1 | Fully Completed | Installation Completed, Devoce location chenged | NA |  | Received
127 | IN-1022944 | PALASHI | L1-L2 improvement FY24 Ph-2, 80 sites | 5 | 13-03-2026 | 13-03-2026 | Converter installation + VIVA BH Survey | 13-03-2026 | 1 | Fully Completed |  | NA |  | Received
128 | BIHAUR0811 | Club Road | BH migration from TTSL to alternate FY25 | 5 | 24-03-2026 | 24-03-2026 | Device Repace | 27-03-2026 | 3 | Migration WIP | Device Issue, 2nd time device issue | NA |  | Received
129 | WEBMUR0455 | Behrampur_007 | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | BTS Survey+ UBR Survey | 2026-04-06 | 1 | Fully Completed |  | NA |  | Received
130 | WEBMUR0444 | Behrampur_09 | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | BTS Survey+ UBR Survey | 2026-04-06 | 1 | Fully Completed |  | NA |  | Received
131 | IN-1038019 | BEHRAMPUR BUS STAND_LIC | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | UBR Survey | 2026-04-06 | 1 | Fully Completed |  | NA |  | Received
132 | 091MURS623014664588 | Bank Of India Limited East | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | Customer Survey | 2026-04-07 | 2 | Fully Completed |  | NA |  | Received
133 | 091BERH6230A0216847 | Directorate of Income Tax (Systems) | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | Customer Survey | 2026-04-06 | 1 | Fully Completed |  | NA |  | Received
134 | 091BERH6230A0042800 | HDFC Bank Limited | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | Customer Survey | 2026-04-07 | 2 | Fully Completed |  | NA |  | Received
135 | 091MURS623008350095 | ICICI Bank Limited | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | Customer Survey | 2026-04-07 | 2 | Fully Completed |  | NA |  | Received
136 | 091MURS0300A0205649 | Tata AIG General Insurance Company Limited | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | Customer Survey | 2026-04-07 | 2 | Fully Completed |  | NA |  | Received
137 | 091MURS623034632666 | SBI FUNDS MANAGEMENT LIMITED | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | Customer Survey | 2026-04-07 | 2 | Fully Completed |  | NA |  | Received
138 | 091BERH623014548591 | INDIAN BANK Erstwhile Allahabad Bank | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | Customer Survey | 2026-04-07 | 2 | Fully Completed |  | NA |  | Received
139 | 091BEHA623034403800 | BANK OF BARODA | Emergency Relocation | 3 | 2026-06-04 | 2026-06-04 | Customer Survey | 2026-04-07 | 2 | Fully Completed |  | NA |  | Received
140 | BIHVAI0387 | LALGANJ_BH | RF platform migration: Cambium 100 to 450 | 5 | 15-04-2026 | 16-04-2026 | BTS Dismantle | 17-04-2026 | 1 | Fully Completed |  | NA |  | Received
141 | 091ASAN623007844047 | HDFC Securities Limited | Multicast customer migration from PMP to | 5 | 18-04-2026 | 21-04-2026 | Customer Dismantle | 21-04-2026 | 1 | Fully Completed |  | NA |  | Received
142 | 3331253686 | HDFC Securities Limited | Multicast customer migration from PMP to | 5 | 28-01-2026 | 29-01-2026 | Customer Dismantle | 29-01-2026 | 1 | Fully Completed |  | NA |  | Received
143 | WEBHOO2220 | Dankuni North-2 | BS Augment: UBR Backhaul to Direct FY24 | 5 | 21-04-2026 | 22-04-2026 | BTS Dismantle | 23-04-2026 | 1 | Fully Completed |  | NA |  | Received
144 | WEBHOO2220 to WEBHOO0196 | Dankuni North-2 to Uttarpara | BS Augment: UBR Backhaul to Direct FY24 | 5 | 21-04-2026 | 22-04-2026 | UBR Dismantle | 23-04-2026 | 1 | Fully Completed |  | NA |  | Received
145 | OR3091 | CIVIL TOWNSHIP-3 | UBR BH cap aug 48 BS FY26 | 5 | 26-04-2026 | 27-04-2026 | UBR Installation | 2026-05-02 | 5 | Fully Completed |  | NA |  | Received
146 | OR3091 | CIVIL TOWNSHIP-3 | UBR BH cap aug 48 BS FY26 | 5 | 26-04-2026 | 27-04-2026 | UBR Alingment | 2026-02-06 | 5 | Fully Completed |  | NA |  | Received
147 | WEBHOO2220 | Dankuni North-2 | BS Augment: UBR Backhaul to Direct FY24 | 5 | 21-04-2026 | 22-04-2026 | Cable Discunnect | 23-04-2026 | 1 | Fully Completed |  | NA |  | Received
148 | OR3091 | CIVIL TOWNSHIP-3 | UBR BH cap aug 48 BS FY26 | 5 | 26-04-2026 | 27-04-2026 | UBR Migration | 2026-02-05 | 5 | Fully Completed |  | NA |  | Received
149 | IN-1235018 | Rasapunja Bongram | Just‑In‑Time (JIT) Network Rollout | 3 | 2026-05-05 | 2026-05-06 | BTS Survey | 2026-05-06 | 1 | Fully Completed |  | NA |  | Received
150 | 091JEHA623034677044 | PUNJAB NATIONAL BANK | Emergency Relocation | 5 | 2026-05-06 | 2026-05-07 | Customer Survey | 2026-05-08 | 1 | Fully Completed |  | NA |  | Received
151 | 091JEHA6230A0341237 | HDFC Bank Limited | Emergency Relocation | 5 | 2026-05-06 | 2026-05-07 | Customer Survey | 2026-05-08 | 1 | Fully Completed |  | NA |  | Received
152 | 091JEHA623037551716 | TCS PASSPORT SEVA PROJECT | Emergency Relocation | 5 | 2026-05-06 | 2026-05-07 | Customer Survey | 2026-05-08 | 1 | Fully Completed |  | NA |  | Received
153 | 091JEHA6230A0145193 | HDFC LIFE INSURANCE COMPANY LIMITED | Emergency Relocation | 5 | 2026-05-06 | 2026-05-07 | Customer Survey | 2026-05-08 | 1 | Fully Completed |  | NA |  | Received
154 | IN-2004474 | BIGT10213 | Emergency Relocation | 5 | 2026-05-06 | 2026-05-07 | BTS Survey | 2026-05-09 | 2 | Fully Completed |  | NA |  | Received
155 | ID-1001214 | JEHANABAD | Emergency Relocation | 5 | 2026-05-06 | 2026-05-07 | BTS Survey | 2026-05-08 | 1 | Fully Completed |  | NA |  | Received
156 | ORIJHA0205 | Hotel_Yogendra_Jharsuguda | ZTS Relocation FY 24 | 5 | 2026-05-08 | 25-05-2026 | BTS Dismantle | 29-05-2026 | 4 | Fully Completed | Access Issue | NA |  | Received
157 | ORIJHA0205 to ORIJHA0586 | Hotel_Yogendra_Jharsuguda to IncomeTax_GSM | ZTS Relocation FY 24 | 5 | 2026-05-08 | 25-05-2026 | UBR Dismantle | 29-05-2026 | 4 | Fully Completed | Access Issue | NA |  | Received
158 | BIHMUZ0407 | MIT Vikas | RF platform migration: Cambium 100 to 45 | 5 | 2026-05-11 | 2026-05-12 | BTS Dismantle | 14/05/2026 | 2 | Fully Completed | PO WIP | NA |  | Received
159 | 091MUZA623030330799 | Berger Paints India Limited | RF platform migration: Cambium 100 to 45 | 5 | 14-05-2026 | 14-05-2026 | Cambium 100 Dismantle | 14-05-2026 | 1 | Fully Completed |  | NA |  | Received
160 | 091MUZA623030330799 | Berger Paints India Limited | RF platform migration: Cambium 100 to 45 | 5 | 14-05-2026 | 14-05-2026 | Cambium 450i Dismantle | 14-05-2026 | 1 | Fully Completed |  | NA |  | Received
161 | BIHQBG0303 | Station Road Begusarai | UBR BH cap aug 48 BS FY26 | 5 | 17-05-2026 | 18/05/2026 | UBR Installation | 20/05/2026 | 2 | Migration WIP | WCC Hold | NA |  | Received
162 | BIHDAR0781 | Rahamganj | ZTS Relocation FY26 Ph-2 | 5 | 2026-01-06 | 2026-04-06 | UBR Survey | 2026-06-06 | 2 | Fully Completed |  | NA |  | Received
163 | WEBHOW0260 | Liluah Station South | CX4 to Conventional BH FY 25 | 5 | 16/05/2026 | 17/05/2026 | UBR Dismantle | 20/05/2026 | 3 | Fully Completed |  | NA |  | Received
164 | ID-1009670 | Arwal | UBR BH capacity augmentation of 50 BS | 3 | 25/05/2026 | 26/05/2026 | UBR LOS Survey | 26/05/2026 | 1 | Fully Completed |  | NA |  | Not Receive
165 | IN-2004857 | BIGT10412 | CX4 to conventional backhaul PH 3 | 3 | 25/05/2026 | 29-05-2026 | BTS Survey | 29-05-2026 | 3 | Dropped | Safety issue | NA |  | Received
166 | JHARAN0224 | Namkum | Emergency Relocation | 5 | 26/25/2026 | 27/25/2026 | UBR Installation | 27/25/2026 | 2 | Fully Completed |  | NA |  | Received
167 | TAJHRAN0087 to JHARAN0224 | Tatisilvai to Namkum | Emergency Relocation | 5 | 26-05-2026 | 27-05-2026 | UBR Installation | 27-05-2026 | 1 | Fully Completed |  | NA |  | Received
168 | TAJHRAN0087 to JHARAN0224 | Tatisilvai to Namkum | Emergency Relocation | 5 | 27-05-2026 | 28-05-2026 | Switch Installation | 28-05-2026 | 2 | Fully Completed |  | NA |  | Received
169 | VFJHDNB0156 | Jharia | Just‑In‑Time (JIT) Network Rollout | 3 | 21-05-2026 | 28/05/2026 | BTS Survey | 2026-06-01 | 1 | Fully Completed |  | NA |  | Received
170 | BIHDAR0781 | Rahamganj | ZTS Relocation FY26 Ph-2 | 5 | 2026-06-01 | 2026-06-04 | UBR Installation | 2026-06-06 | 2 | Migration WIP |  | NA |  | Received
171 | BIHARA0003 | Forbisganj | Just‑In‑Time (JIT) Network Rollout | 5 | 2026-06-02 | 2026-06-03 | Switch Installation | 2026-06-06 | 3 | Migration WIP |  |  |  | Received
172 | BR/HA/VO/0591 | Kathar Tola | Just‑In‑Time (JIT) Network Rollout | 2 | 2026-06-02 | 2026-06-03 | BTS Survey | 2026-06-05 | 2 | Fully Completed |  |  |  | Received
173 | ORIBAR0053 | Maharaja | T34P-Switch replacement FY25 | 5 | 2026-06-04 | 2026-10-06 | UBR Survey | 15-06-2026 | 5 | Fully Completed |  | NA |  | Received
174 | ORIBAR0053 | Maharaja | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-10-06 | Switch Installation | 15-06-2026 | 5 | Fully Completed |  | NA |  | Received
175 | WEBHOO0195 | SINGUR | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-06-05 | UBR LOS Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
176 | JHALOH0178 | Lohardaga | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-06-05 | BTS Survey | 2026-06-08 | 3 | Issue/Stuck |  | NA |  | Received
177 | BR/PA/AT/17693 | Pakaur (M) | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 17-06-2026 | BTS Survey | 15-06-2026 | 8 | Fully Completed | Work load high | NA |  | Received
178 | IN-2036076 | ORGT10878 | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 17-06-2026 | BTS Survey | 16-06-2026 | 8 | Fully Completed | Work load high | NA |  | Received
179 | IN-2004488 | BIGT10220 | ZTS Relocation FY26 Ph-2 | 2 | 2026-06-04 | 2026-06-05 | BTS Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
180 | 091RANC623036796736 | UNION BANK OF INDIA | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
181 | 091RANC623036213480 | Bank of India | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
182 | 091SITA0300A0404713 | BAJAJ LIFE INSURANCE LIMITED | ZTS Relocation FY26 Ph-2 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
183 | 091SITA6230A0420537 | Ujjiban | ZTS Relocation FY26 Ph-2 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
184 | 091DUMR6230A0066627 | Axis Bank Limited | ZTS Relocation FY26 Ph-2 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
185 | 091SITA6230A0411772 | IndusInd | ZTS Relocation FY26 Ph-2 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
186 | 091SITA623037548460 | TCS (PASSPORT SEVA PROJECT) | ZTS Relocation FY26 Ph-2 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
187 | 091BATH0300A0071211 | Jubilant Foodworks Limited | ZTS Relocation FY26 Ph-2 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
188 | 091SITA623016904624 | UNION BANK OF INDIA | ZTS Relocation FY26 Ph-2 | 2 | 2026-06-04 | 2026-06-05 | Customer Survey | 2026-06-08 | 3 | Fully Completed |  | NA |  | Received
189 | 091PAKU6230A0220903 | IndusInd Bank Limited | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 13-06-2026 | Customer Survey | 15-06-2026 | 5 | Fully Completed |  | NA |  | Received
190 | 091PAKU623013716594 | STATE BANK OF INDIA | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-06-10 | Customer Survey | 15-06-2026 | 5 | Fully Completed |  | NA |  | Received
191 | 091CUTT623034701608 | UNION BANK OF INDIA- erstwhile CB | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-06-07 | Customer Survey | 2026-06-07 | 9 | Fully Completed |  | NA |  | Received
192 | 3331211805 | Axis Bank Limited | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-06-07 | Customer Survey | 2026-06-07 | 9 | Fully Completed |  | NA |  | Received
193 | 091JAJP623037541580 | TCS PASSPORT SEVA PROJECT | CX4 to conventional backhaul PH 3 | 2 | 2026-06-04 | 2026-06-07 | Customer Survey | 2026-06-07 | 9 | Fully Completed |  | NA |  | Received
194 | ORIKHU0857 | UW_Orissa_0630_Jatni (Khasmahal) | Emergency Relocation | 3 | 2026-06-05 | 2026-06-08 | Customer Survey | 15-06-2026 | 7 | Fully Completed |  | NA |  | Received
195 | 091BHUB623032725603 | UNION BANK OF INDIA_erstwhile AB | Emergency Relocation | 3 | 2026-06-05 | 2026-06-08 | BTS Syrvey | 15-06-2026 | 7 | Fully Completed |  | NA |  | Received
196 | 091KHOR623035953409 | Manappuram Finance Limited | Emergency Relocation | 3 | 2026-06-05 | 2026-06-08 | Customer Survey | 15-06-2026 | 7 | Fully Completed |  | NA |  | Received
197 | 091KHOR6230A0160300 | SBI Life Insurance Company Limited | Emergency Relocation | 3 | 2026-06-05 | 2026-06-08 | Customer Survey | 15-06-2026 | 7 | Fully Completed |  | NA |  | Received
198 | 091JATN623036120242 | Indian Bank | Emergency Relocation | 3 | 2026-06-05 | 2026-06-08 | Customer Survey | 15-06-2026 | 7 | Fully Completed |  | NA |  | Received
199 | TCLBSNL14112017-051774 | KASBA | Non Performing BS Optimization Ph-10A | 5 | 2026-06-05 | 25-08-2026 | BTS Dismantle | 25-08-2026 | 1 | Fully Completed | Access Issue // Completed | NA |  | Received
200 | IN-1023559 | SAKUNTALA_PARK | Emergency Relocation | 3 | 2026-06-05 | 2026-06-05 | BTS Survey | 2026-06-06 | 1 | Fully Completed |  | NA |  | Received
201 | 091KOLK623010952524 | Axis Bank Limited | Emergency Relocation | 3 | 2026-06-05 | 2026-06-06 | Customer Survey | 2026-06-08 | 2 | Fully Completed |  | NA |  | Received
202 | 091KOLK623010859113 | INDIAN OVERSEAS BANK | Emergency Relocation | 3 | 2026-06-05 | 2026-06-06 | Customer Survey | 2026-06-08 | 2 | Fully Completed |  | NA |  | Received
203 | 091KOLK623033494181 | Ipca Laboratories Limited | Emergency Relocation | 3 | 2026-06-05 | 2026-06-06 | Customer Survey | 2026-06-08 | 2 | Fully Completed |  | NA |  | Received
204 | 091KOLK623011868015 | HDFC Bank Limited | Emergency Relocation | 3 | 2026-06-05 | 2026-06-06 | Customer Survey | 2026-06-08 | 2 | Fully Completed |  | NA |  | Received
205 | 091KOLK030038626528 | HDB Financial Services Limited | Emergency Relocation | 3 | 2026-06-05 | 2026-06-06 | Customer Survey | 2026-06-08 | 2 | Fully Completed |  | NA |  | Received
206 | BR/LO/VO/0671 to JHALOH0178 | KARTIK NAGAR JURIYA to Lohardaga | CX4 to conventional backhaul PH 3 | 3 | 25-06-2026 | 26-06-2026 | UBR LOS Survey | 27-06-2026 | 2 | Fully Completed |  | NA |  | Received
207 | BIHPAT1042 | Exhibition Road | Low Potential BS & Sector Dismantling 70 | 5 | 24-06-2026 | 24-06-2026 | BTS Dismantle | 26-06-2026 | 1 | Site Complete Status |  | NA |  | Received
208 | BHBS000009 | AIPL- Rajgir bazaar | T34P-Switch replacement FY25 | 5 | 23-06-2026 | 24-06-2026 | Switch Installation | 25-06-2026 | 1 | Issue/Stuck | Device Foulty | NA |  | Received
209 | OR3091 | Civil Township-3 | UBR BH cap aug 48 BS FY26 | 5 | 23-06-2026 | 2026-01-05 | UBR Dismantle | 2026-01-07 | 12 | Fully Completed | PO WIP/ LC Required | NA |  | Received
210 | 091RANC6230A0005128 | Bennett Coleman and Company Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
211 | 091KOLK0300Z0000005 | Bharti AXA Life Insurance Company Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
212 | 091KOLK623010230734 | Export Import Bank of India | P2P to PMP Phase 6 | 3 | 25-06-2026 | 2026-01-06 | Customer PMP Survey | 2026-01-07 | 1 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
213 | 091RANC623037242541 | AU SMALL FINANCE BANK LIMITED. | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
214 | 091RANC623035334133 | Cholamandalam MS General Insurance Company Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
215 | 091PATN623029659429 | UNION BANK OF INDIA | P2P to PMP Phase 6 | 3 | 25-06-2026 | 28-06-2026 | Customer PMP Survey | 29-06-2026 | 1 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
216 | 091MOTI6230A0058036 | Tata AIA Life Insurance Company Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 | 2026-11-08 | Customer PMP Survey | 13-08-2026 | 2 | Installatio WIP | PO WIP/ LC Required/ Device required | NA |  | Not Receive
217 | 091RANC6230A0090015 | ITC Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
218 | 091BOLP623037545999 | TCS (PASSPORT SEVA PROJECT) | P2P to PMP Phase 6 | 3 | 25-06-202602-09-2026 | 2026-02-09 | Customer PMP Survey | 2026-02-09 | 1 | Installatio WIP | PO WIP/ LC Required \ Device required | NA |  | Not Receive
219 | 091BUXA6230A0064103 | Tata AIA Life Insurance Company Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
220 | 091RAIG623037545807 | TCS (PASSPORT SEVA PROJECT) | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
221 | 091PATN623012021478 | Yes Bank Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 | 28-06-2026 | Customer PMP Survey | 30-06-2026 | 2 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
222 | 091PATN030037202509 | Prama Hikvision India Private Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 | 28-06-2026 | Customer PMP Survey | 30-06-2026 | 2 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
223 | 091DARB6230A0113537 | Bajaj Allianz Life Insurance Company Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 | 2026-11-08 | Customer PMP Survey | 2026-12-08 | 1 | Installatio WIP | PO WIP/ LC Required/ Device required | NA |  | Not Receive
224 | 091HOOG623035555880 | PUNJAB NATIONAL BANK | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
225 | 091JALP623031780021 | Bajaj Finance Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 |  | Customer PMP Survey |  |  | Pending/YTS | PO WIP/ LC Required | NA |  | Not Receive
226 | BIHQBG0303 to BIHBEG1767 | Station Road Begusarai to LOHIYA NAGAR | Emergency Relocation | 3 | 2026-07-03 | 2026-07-04 | UBR LOS Survey | 2026-07-07 | 3 | Fully Completed |  | NA |  | Received
227 | 091BEGU623034874635 | Bank of Baroda | Emergency Relocation | 3 | 2026-07-03 | 2026-07-07 | Customer PMP Survey | 2026-07-07 | 1 | Fully Completed |  | NA |  | Received
228 | IN-1063021 to WEBMUR0444 | KALILAPUR to Behrampur_09 | Emergency Relocation | 3 | 2026-07-03 | 2026-07-06 | UBR LOS Survey | 2026-09-07 | 2 | Fully Completed |  | NA |  | Received
229 | IN-1063021 to IN-1038019 | KALILAPUR to BEHRAMPUR BUS STAND_LIC | Emergency Relocation | 3 | 2026-07-03 | 2026-07-06 | UBR LOS Survey | 2026-09-07 | 2 | Fully Completed |  | NA |  | Received
230 | IN-1132672 to WEBMUR0444 | KARWALA ROAD to Behrampur_09 | Emergency Relocation | 3 | 2026-07-03 | 2026-07-06 | UBR LOS Survey | 2026-09-07 | 2 | Fully Completed |  | NA |  | Received
231 | IN-1132672 to IN-1038019 | KARWALA ROAD to BEHRAMPUR BUS STAND_LIC | Emergency Relocation | 3 | 2026-07-03 | 2026-07-06 | UBR LOS Survey | 2026-09-07 | 2 | Fully Completed |  | NA |  | Received
232 | IN-2004474 | BIGT10213 | Emergency Relocation | 5 | 15-06-2026 | 2026-11-07 | Sector Installation | 14-07-2026 | 3 | Fully Completed | device received-18-06-2026/ Honey Bee Issue | NA |  | Received
233 | IN-2004474 | BIGT10213 | Emergency Relocation | 5 | 15-06-2026 | 2026-11-07 | Switch Installation | 15-07-2026 | 4 | Fully Completed | device received-18-06-2026/ Honey Bee Issue | NA |  | Received
234 | WEBMUR0444 | Behrampur_09 | Emergency Relocation | 5 | 18-07-2026 | 20-07-2026 | BTS installation | 31-07-2026 | 6 | Fully Completed | Installation Done -24-07-2026 , AT done- 29-07-2026 | NA |  | Received
235 | IN-1038019 | BEHRAMPUR BUS STAND_LIC | Emergency Relocation | 5 | 18-07-2026 | 20-07-2026 | UBR Installation | 2026-04-08 | 4 | Fully Completed | AT Done -04-08-2026 | NA |  | Received
236 | BR/PT/AT/11219 | Khagaul | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | BTS Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
237 | BH5076 | SALEMPUR | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | BTS Survey | 2026-07-08 | 3 | Fully Completed |  | NA |  | Received
238 | BH5076 to BIHSAR0347 | SALEMPUR to Rajendra College More | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | UBR LOS Survey | 2026-07-08 | 3 | Fully Completed |  | NA |  | Received
239 | BR/PT/AT/11219 to BIHPAT0299 | SALEMPUR to Rajendra College More | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | UBR LOS Survey | 2026-07-08 | 3 | Fully Completed |  | NA |  | Received
240 | 091PATN623015574416 | HDFC BANK LIMITED | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
241 | 091PATN623013136286 | STATE BANK OF INDIA | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
242 | 091CHHA6230A0420539 | Ujjivan Bank | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
243 | 091DANA6230A0215281 | Tata AIA Life Insurance Company Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
244 | 091PATN623036134610 | HDFC Bank Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
245 | 091PATN6230A0007953 | DCB Bank Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
246 | 091PATN623035840778 | Sony India Private Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
247 | 091PATN030038256628 | ACC Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
248 | 091KHAG0300A0382199 | Kotak Mahindra Bank Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-04-08 | Customer Survey | 2026-04-08 | 3 | Fully Completed |  | NA |  | Received
249 | 091CHHA6230A0385075 | BAJAJ LIFE INSURANCE LIMITED | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
250 | 091SARA623013806682 | SBI Life Insurance Company Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
251 | 091SARA623035691206 | JANA SMALL FINANCE BANK LIMITED. | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
252 | 091CHHA6230A0214624 | Tata AIA Life Insurance Company Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
253 | 091CHHA623033674361 | AGEAS FEDERAL LIFE INSURANCECOMPANY LIMITED | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
254 | 091CHHA623037547433 | TCS PASSPORT SEVA PROJECT | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
255 | 091CHHA0300A0139631 | ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
256 | 091CHHA623017545879 | ICICI Bank Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
257 | 091CHHA0300A0192636 | HDB Financial Services Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
258 | 091SARA030037129281 | Jubilant Foodworks Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
259 | 091CHHA6230A0216994 | Directorate of Income Tax Systems | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
260 | 091CHHA6230Z0000003 | Bharti AXA Life Insurance Company Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
261 | 091CHHA623017215257 | PNB METLIFE INDIA INSURANCE COMPANY LIMITED | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
262 | 091SARA623013207644 | State Bank of India | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
263 | 091NADI623009624775 | Axis Bank Limited | High Colo Opex BTS & ZTS relocation | 3 | 2026-03-08 | 2026-05-08 | Customer Survey | 2026-09-08 | 4 | Fully Completed |  | NA |  | Received
264 | 091KOLK623005767629 | Tata Motors Finance Solution Limited | Multicast customer migration from PMP to | 5 | 2026-02-09 | 2026-03-09 | P2P link dismantling | 2026-03-09 | 1 | Fully Completed |  | NA |  | Not Receive
265 | 091KOLK623010230734 | Export Import Bank of India | P2P to PMP Phase 6 | 3 | 25-06-2026 | 2026-08-20 | Customer PMP Survey | 2026-08-20 | 1 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
266 | 091PATN623029659429 | UNION BANK OF INDIA | P2P to PMP Phase 6 | 3 | 25-06-2026 | 30-08-2026 | Customer Installation | 30-08-2026 | 1 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
267 | 091PATN623012021478 | Yes Bank Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 | 30-08-2026 | Customer Installation | 30-08-2026 | 2 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
268 | 091PATN030037202509 | Prama Hikvision India Private Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 | 30-08-2026 | Customer Installation | 30-08-2026 | 2 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
269 | 091KOLK623010230734 | Export Import Bank of India | P2P to PMP Phase 6 | 3 | 25-06-2026 | 2026-08-20 | Migartion | 2026-08-20 | 1 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
270 | 091PATN623029659429 | UNION BANK OF INDIA | P2P to PMP Phase 6 | 3 | 25-06-2026 | 30-08-2026 | Migartion | 31-08-2026 | 1 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
271 | 091PATN623012021478 | Yes Bank Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 | 30-08-2026 | Migartion | 31-08-2026 | 2 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
272 | 091PATN030037202509 | Prama Hikvision India Private Limited | P2P to PMP Phase 6 | 3 | 25-06-2026 | 30-08-2026 | Migartion | 31-08-2026 | 2 | Fully Completed | PO WIP/ Device Required | NA |  | Not Receive
273 | ID-1009670 | Arwal | UBR BH capacity augmentation of 50 BS | 5 | 2026-05-08 | 2026-07-08 | UBR Installation | 2026-10-08 | 3 | Issue/Stuck | Safety Issue | NA |  | Not Receive
274 | WEBHOW0264 | RamRajaTala | UBR BH capacity augmentation of 50 BS | 1 | 13--08-2026 | 2026-08-16 | UBR Alingment | 2026-08-16 | 1 | Fully Completed |  | NA |  | Not Receive
275 | WEBNOR0599 | Kachrapara | UBR BH capacity augmentation of 50 BS | 1 | 2026-08-19 | 2026-08-23 | UBR BH alignment | 2026-08-23 | 1 | Fully Completed |  | NA |  | Not Receive
276 | WEBNOR0602 | Kalyani | UBR BH capacity augmentation of 50 BS | 1 | 2026-08-19 | 2026-08-23 | UBR BH migration | 2026-08-23 | 1 | Fully Completed |  | NA |  | Not Receive
277 | BIHQBG0303 | Station Road Begusarai | Emergency Relocation | 5 | 26-08-2026 | 28-08-2026 | UBR Installation | 2020-01-09 | 4 | AT WIP |  | NA |  | Not Receive
278 | BIHQBG0303 | Station Road Begusarai | Emergency Relocation | 5 | 26-08-2026 | 28-08-2026 | Switch Installation | 2020-01-09 | 4 | Fully Completed |  | NA |  | Not Receive
279

## Team Details
Location | FE Name | City | Designation
Bihar | Pintu Kumar | Patna | Field Enginner
| Aman Kumar | Patna | Technician
Location | FE Name | City | Designation
West Bengal | Ajay Kumar Shaw | Kolkata | Field Enginner
| Anil Chowdhury | Kolkata | Field Enginner
Location | FE Name | City | Designation
Jharkhand | Manoj Kumar | Kolkata | Field Enginner
Location | FE Name | City | Designation
Odisha | Rahul Ranjan Behera | Cuttack | Field Enginner
| Rakesh Rature | Cuttack | Technician