## Master Sheet
Region | State | Project Name | Delivery Track | BTS/Customer | Site ID | BTS/Customer Name | Activity | Loading Date from WI team | Permission Recieved Date | Complete Date | Actual TAT | Aging | WI TAT-Standard | TAT Remarks | Status | Remarks | WO Status | WO Remarks
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORICUT0096 | CTK_08_KALYAN_NAGAR | UBR BH survey | 2025-07-22 | 2025-07-22 | 2025-07-28 | 6 | 419 | 3 | Delayed due to FE ePTW not generated | Survey Completed | LOS feasible from IM Site- Andarpur_ORIQBC0137 | Released
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORIQBC0117 | Pota_Pokhari | UBR BH survey | 2025-07-22 | 2025-07-22 | 2025-07-28 | 6 | 419 | 3 | Delayed due to FE ePTW not generated | Survey Completed | LOS feasible from IM Site- Andarpur_ORIQBC0137 | Released
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORIQBC0217 | Nayasadak | UBR BH survey | 2025-07-22 | 2025-07-22 | 2025-07-28 | 6 | 419 | 3 | Delayed due to FE ePTW not generated | Survey Completed | LOS feasible from IM Site- Andarpur_ORIQBC0137 | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | BTS | OR3007 | GHASISAHI-1 | Sector Replacement | 2025-07-28 | 2025-07-31 | 2025-08-01 | 1 | 410 | 5 | Within TAT | Fully Completed | AT & SM testing completed | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | BTS | ORIMAY0299 | Baripada_highway | Sector Replacement | 2025-07-28 | 2025-07-31 | 2025-08-05 | 5 | 410 | 5 | Within TAT | Fully Completed | AT & SM testing completed | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | BTS | ORIGAN0157 | Berhampur3 (station road) | Sector Replacement | 2025-08-22 | 2025-08-22 | 2025-08-26 | 4 | 388 | 5 | Within TAT | Fully Completed | AT & SM testing completed | Released
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORICUT0096 | CTK_08_KALYAN_NAGAR | Installation - UBR BH | 2025-08-25 | 2025-08-26 | 2025-09-01 | 6 | 384 | 5 | Delayed due to UBR tac dependency | Fully Completed | AT completed | Released
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORIQBC0117 | Pota_Pokhari | Installation - UBR BH | 2025-08-25 | 2025-08-26 | 2025-09-06 | 11 | 384 | 5 | Delayed due to UBR tac dependency | Fully Completed | AT completed | Released
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORIQBC0217 | Nayasadak | Installation - UBR BH | 2025-08-25 | 2025-08-26 | 2025-09-05 | 10 | 384 | 5 | Delayed due to UBR tac dependency | Fully Completed | AT completed | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | Customer | 091KHOR623036114789 | Indian Bank | Survey - Customer (PMP) | 2025-08-21 | 2025-11-12 | 2025-11-12 | 0 | 306 | 5 | Within TAT | Survey Completed | PMP Feasible with 3 mtr existing pole | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | Customer | 091KHOR623036114789 | Indian Bank | Installation - Customer | 2025-08-21 | 2025-11-12 | 2025-12-17 | 35 | 306 | 5 | TAT Missed due to material availibility | Fully Completed | Link under stability | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | Customer | 091MAYU623016899749 | UNION BANK OF INDIA | Survey - Customer (PMP) | 2025-08-21 | 2025-09-05 | 2025-09-09 | 4 | 374 | 5 | Within TAT | Survey Completed | Feasible in PMP | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | Customer | 091MAYU623016899749 | UNION BANK OF INDIA | Installation - Customer | 2025-08-21 | 2025-09-05 | 2025-09-09 | 4 | 374 | 5 | Within TAT | Fully Completed |  | Released
East | Orissa | Emergency Relocation | BTS | BTS | OR/BE/VF/0089 | Rangilunda | Survey - BS(PMP) | 2025-08-29 | 2025-08-30 | 2025-08-31 | 1 | 380 | 2 | Within TAT | Survey Completed | Report shared | Released
East | Orissa | Emergency Relocation | UBR | BTS | OR/BE/VF/0089 | Rangilunda | UBR BH survey | 2025-08-29 | 2025-08-30 | 2025-08-31 | 1 | 380 | 2 | Within TAT | Survey Completed | Report shared, LOS Feasible | Released
East | Orissa | Emergency Relocation | BTS | BTS | OR3048 | Patia | Survey - BS(PMP) | 2025-08-29 | 2025-09-06 | 2025-09-08 | 2 | 373 | 2 | Within TAT | Survey Completed | Report shared | Released
East | Orissa | Emergency Relocation | BTS | BTS | OR/MA/VF/0010 | Gudakata | Survey - BS(PMP) | 2025-09-09 | 2025-09-10 | 2025-09-11 | 1 | 369 | 2 | Within TAT | Survey Completed | Report shared | Released
East | Orissa | Emergency Relocation | UBR | BTS | OR/MA/VF/0010 | Gudakata | UBR BH survey | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2 | 369 | 2 | Within TAT | Survey Completed | Report shared, LOS Feasible | Released
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORICUT0096 | CTK_08_KALYAN_NAGAR | Migration - UBR BH | 2025-09-11 | 2025-09-13 | 2025-09-14 | 1 | 366 | 2 | Within TAT | PE Done |  | Released
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORIQBC0117 | Pota_Pokhari | Migration - UBR BH | 2025-09-11 | 2025-09-13 | 2025-09-14 | 1 | 366 | 2 | Within TAT | PE Done |  | Released
East | Orissa | CX4 to Conventional BH FY 25 | UBR | BTS | ORIQBC0217 | Nayasadak | Migration - UBR BH | 2025-09-11 | 2025-09-13 | 2025-09-14 | 1 | 366 | 2 | Within TAT | PE Done |  | Released
East | Orissa | Emergency Relocation | BTS | BTS | OR/BE/VF/0089 | Rangilunda | Installation - BS(PMP) | 2025-09-16 | 2025-10-15 | 2025-12-26 | 72 | 334 | 2 | TAT Missed for material change | Fully Completed | AT Completed and SM Testing done | Released
East | Orissa | Emergency Relocation | UBR | BTS | OR/BE/VF/0089 | Rangilunda | Installation - UBR BH | 2025-09-16 | 2025-10-15 | 2025-12-26 | 72 | 334 | 2 | TAT Missed for material change | Fully Completed | AT Done | Released
East | Orissa | Emergency Relocation | BTS | BTS | OR3048 | Patia | Installation - BS(PMP) | 2025-09-16 | 2025-10-13 | 2025-11-03 | 21 | 336 | 2 | TAT Missed due to switch faulty | Fully Completed | AT Completed and SM Testing done | Released
East | Orissa | Emergency Relocation | BTS | BTS | OR/MA/VF/0010 | Gudakata | Installation - BS(PMP) | 2025-09-16 | 2025-10-20 | 2025-12-31 | 72 | 329 | 2 | TAT Missed due to switch faulty | Fully Completed | AT Completed and SM Testing done | Released
East | Orissa | TTL Rollback | UBR | BTS | ORIQBC0117 | Pota_Pokhari | Dismantle - UBR BH | 2025-10-03 | 2025-10-05 | 2025-10-15 | 10 | 344 | 7 | TAT Missed due to one end pending only | Dismantle completed | Material handovered to RIPL on 17-Nov-25 | Released
East | Orissa | TTL Rollback | UBR | BTS | ORIQBC0217 | Nayasadak | Dismantle - UBR BH | 2025-10-03 | 2025-10-05 | 2025-10-11 | 6 | 344 | 7 | Within TAT | Dismantle completed | FRN Done | Released
East | Orissa | Emergency Relocation | UBR | BTS | IN-3129907 | Teachers colony | UBR BH survey | 2025-10-04 | 2025-10-05 | 2025-10-07 | 2 | 344 | 2 | Within TAT | Survey Completed | Report shared,LOS Feasible | Released
East | Orissa | Emergency Relocation | BTS | BTS | IN-3129907 | Teachers colony | Survey - BS(PMP) | 2025-10-04 | 2025-10-05 | 2025-10-07 | 2 | 344 | 2 | Within TAT | Survey Completed | Report shared | Released
East | Orissa | Emergency Relocation | Customer | Customer | 091MAYU623014831595 | Central Bank Of India | Survey - Customer | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2 | 343 | 2 | Within TAT | Survey Completed | Report shared, Feasible with 3 mtr new pole | Released
East | Orissa | Emergency Relocation | Customer | Customer | 091BARI6230A0234615 | HDFC LIFE INSURANCE COMPANY LIMITED | Survey - Customer | 2025-10-06 | 2025-10-06 | 2025-10-09 | 3 | 343 | 2 | Within TAT | Survey Completed | Report shared, Feasible with 3 mtr new pole | Released
East | Orissa | Emergency Relocation | Customer | Customer | 091BARI623037541482 | TCS PASSPORT SEVA PROJECT | Survey - Customer | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2 | 343 | 2 | Within TAT | Survey Completed | Report shared, Feasible with 6 mtr new pole | Released
East | Orissa | Emergency Relocation | Customer | Customer | 091BARI623034701960 | UNION BANK OF INDIA- erstwhile CB | Survey - Customer | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2 | 343 | 2 | Within TAT | Survey Completed | Report shared, Feasible with 6 mtr new pole | Released
East | Orissa | Emergency Relocation | Customer | Customer | 091BHUB623011070042 | INDIAN OVERSEAS BANK | Survey - Customer | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2 | 343 | 2 | Within TAT | Survey Completed | Report shared, Feasible with 3 mtr existing pole | Released
East | Orissa | Emergency Relocation | Customer | Customer | 091MYSU6230A0219188 | Directorate of Income Tax (Systems) | Survey - Customer | 2025-10-06 | 2025-10-06 | 2025-10-08 | 2 | 343 | 2 | Within TAT | Survey Completed | Report shared, Feasible with 21 mtr existing GBT Mast | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091BURD623013072306 | INDIAN BANK (Erstwhile Allahabad Bank) | Survey - Customer | 2025-10-10 | 2025-11-10 | 2025-11-10 | 0 | 308 | 2 | Within TAT | Survey Completed | PMP Feasible with 3 mtr existing pole | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091HALD623010138390 | UNION BANK OF INDIA_erstwhile AB | Survey - Customer | 2025-10-10 | 2025-11-04 | 2025-11-04 | 0 | 314 | 7 | Within TAT | Survey Completed | PMP not feasible, Link kept on old LM | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091ASAN030038249250 | ACC Limited | Survey - Customer | 2025-10-10 | 2025-11-11 | 2025-11-11 | 0 | 307 | 7 | Within TAT | Survey Completed | PMP Feasible on existing wall mount L-pole | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091CONT6230A0119603 | Bajaj Allianz Life Insurance Company Limited | Survey - Customer | 2025-10-10 | 2025-11-01 | 2025-11-15 | 14 | 317 | 7 | TAT Missed due to material received delayed | Survey Completed | PMP not feasible, Link kept on old LM | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091MEDI623017779572 | BAJAJ FINANCE LTD | Survey - Customer | 2025-10-10 | 2025-11-01 | 2025-11-15 | 14 | 317 | 7 | TAT Missed due to material received delayed | Survey Completed | PMP Feasible with 3 mtr existing pole | Released
East | Orissa | PTP to PMP Conversion 5 | Customer | Customer | 091BHUB623029415318 | ATC Telecom Infrastructure Private Limited | Survey - Customer | 2025-10-10 | 2025-11-01 | 2025-11-10 | 9 | 317 | 7 | TAT Missed due to material received delayed | Survey Completed | PMP Feasible with 3 mtr existing pole | Released
East | Orissa | PTP to PMP Conversion 5 | Customer | Customer | 091BHUB623031266711 | Maruti Suzuki India Ltd | Survey - Customer | 2025-10-10 | 2025-11-04 | 2025-11-04 | 0 | 314 | 7 | Within TAT | Survey Completed | PMP Feasible with 3 mtr existing pole | Released
East | Orissa | PTP to PMP Conversion 5 | Customer | Customer | 091BHUB030037762724 | Ingram Micro India Private Limited | Survey - Customer | 2025-10-10 | 2025-11-10 | 2025-11-11 | 1 | 308 | 7 | Within TAT | Survey Completed | Customer shifted to another location | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | Customer | 091MAYU623016899749 | UNION BANK OF INDIA | Migration-Customer | 2025-11-04 | 2025-11-05 | 2025-11-07 | 2 | 313 | 2 | Within TAT | Migrated |  | Released
East | Orissa | Emergency Relocation | BTS | BTS | IN-3129907 | Teachers colony | Installation - BS(PMP) | 2025-11-08 | 2025-11-16 | 2026-01-04 | 49 | 302 | 2 | TAT Missed due to access issue | Fully Completed | AT Complete & SM testing done | Released
East | Orissa | Emergency Relocation | UBR | BTS | IN-3129907 | Teachers colony | Installation - UBR BH | 2025-11-08 | 2025-11-16 | 2025-12-30 | 44 | 302 | 2 | TAT Missed due to access issue | Fully Completed | Link stable,AT Complete | Released
East | Jharkhand | Emergency Relocation | UBR | BTS | JHABOK0010 | Chaas-01 | Installation - UBR BH | 2025-11-08 | 2025-11-12 | 2025-11-18 | 6 | 306 | 2 | TAT missed for device become faulty | Fully Completed | AT Sheet and snap shared | Released
East | Orissa | PTP to PMP Conversion 5 | Customer | Customer | 091BHUB623031266711 | Maruti Suzuki India Ltd | Installation - Customer | 2025-10-10 | 2025-11-10 | 2025-11-11 | 1 | 308 | 7 | Within TAT | Fully Completed |  | Released
East | Orissa | PTP to PMP Conversion 5 | Customer | Customer | 091BHUB623029415318 | ATC Telecom Infrastructure Private Limited | Installation - Customer | 2025-10-10 | 2025-11-11 | 2025-11-11 | 0 | 307 | 7 | Within TAT | Fully Completed |  | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091BURD623013072306 | INDIAN BANK (Erstwhile Allahabad Bank) | Installation - Customer | 2025-10-10 | 2025-11-18 | 2025-11-20 | 2 | 300 | 7 | Within TAT | Fully Completed |  | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091ASAN030038249250 | ACC Limited | Installation - Customer | 2025-10-10 | 2025-11-11 | 2025-11-11 | 0 | 307 | 7 | Within TAT | Fully Completed |  | Released
East | Orissa | PTP to PMP Conversion 5 | Customer | Customer | 091BHUB623029415318 | ATC Telecom Infrastructure Private Limited | Migration-Customer | 2025-11-13 | 2025-11-14 | 2025-11-14 | 0 | 304 | 2 | Within TAT | Migrated |  | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091MEDI623017779572 | BAJAJ FINANCE LTD | Installation - Customer | 2025-11-15 | 2025-11-15 | 2025-11-20 | 5 | 303 | 7 | TAT missed for device not available | Fully Completed |  | Released
East | Bihar | Radwin 5K Migration - PH-1 | BTS | BTS | 4138 | AURANGABAD-01 | Survey - BS(PMP) | 2025-12-18 | 2025-12-20 | 2026-01-06 | 17 | 268 | 7 | TAT Missed from our end | Survey Completed |  | Released
East | Bihar | Radwin 5K Migration - PH-1 | BTS | BTS | 4138 | AURANGABAD-01 | Installation - BS(PMP) | 2025-12-18 | 2025-12-20 | 2026-01-06 | 17 | 268 | 7 | TAT Missed from our end | Fully Completed | AT Complete, SM testing pending | Released
East | Orissa | Radwin 5K Migration - PH-1 | BTS | BTS | ORIJAG0396 | PPL Colony | Survey - BS(PMP) | 2025-12-18 | 2025-12-20 | 2025-12-25 | 5 | 268 | 7 | Within TAT | Survey Completed |  | Released
East | Orissa | Radwin 5K Migration - PH-1 | BTS | BTS | ORIJAG0396 | PPL Colony | Installation - BS(PMP) | 2025-12-18 | 2025-12-20 | 2025-12-25 | 5 | 268 | 7 | Within TAT | Physical Completed |  | Released
East | Orissa | PTP to PMP Conversion 5 | Customer | Customer | 091BHUB623031266711 | Maruti Suzuki India Ltd | Migration-Customer | 2025-11-18 | 2025-11-18 | 2025-11-19 | 1 | 300 | 7 | Within TAT | Migrated |  | Released
East | Jharkhand | Emergency Relocation | UBR | BTS | JHABOK0010 | Chaas-01 | Migration - UBR BH | 2025-11-25 | 2025-11-29 | 2025-11-30 | 1 | 289 | 2 | Within TAT | Migrated |  | Released
East | Orissa | RF platform migration: Cambium 100 to 45 | Cambium 100 to 450i Replacement + CPE migration | Customer | 091KHOR623036114789 | Indian Bank | Migration-Customer | 2025-12-19 | 2025-12-19 | 2025-12-19 | 0 | 269 | 2 | Within TAT | Migrated |  | Released
East | West Bengal | PTP to PMP Conversion 5 | Customer | Customer | 091ASAN030038249250 | ACC Limited | Migration-Customer | 2025-12-19 | 2025-12-19 | 2025-12-19 | 0 | 269 | 2 | Within TAT | Migrated |  | Released
East | Orissa | Radwin 5K Migration - PH-1 | Customer | Customer | 091JAGA623037282697 | HDFC Bank Limited | Installation - Customer | 2026-01-13 | 2026-01-20 | 2026-03-17 | 56 | 237 | 7 | TCL GA was pending | Fully Completed |  | Released
East | Orissa | Radwin 5K Migration - PH-1 | Customer | Customer | 091PARA0300A0159727 | Adani Wilmar Limited | Survey - Customer | 2026-01-13 | 2026-01-20 | 2026-03-13 | 52 | 237 | 7 | TCL GA was pending | Survey Completed | Not feasible in PMP, so kept on old LM-P2P | Released
East | Orissa | Radwin 5K Migration - PH-1 | Customer | Customer | 091KEND623036786991 | Tata AIA Life Insurance Company Limited | Installation - Customer | 2026-01-13 | 2026-01-20 | 2026-03-17 | 56 | 237 | 7 | TCL GA was pending | Fully Completed |  | Released
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA6230A0296946 | Directorate of Income Tax Systems | Installation - Customer | 2026-01-13 | 2026-01-20 | 2026-03-25 | 64 | 237 | 7 | TCL GA was pending | Fully Completed |  | Released
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA623017007536 | UNION BANK OF INDIA | Installation - Customer | 2026-01-13 | 2026-01-20 | 2026-03-25 | 64 | 237 | 7 | TCL GA was pending | Fully Completed |  | Released
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA0300A0312332 | SHRIRAM FINANCE LIMITED | Installation - Customer | 2026-01-13 | 2026-01-20 | 2026-03-25 | 64 | 237 | 7 | TCL GA was pending | Fully Completed |  | Released
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA623038521612 | Tata AIA Life Insurance Company Limited | Installation - Customer | 2026-01-13 | 2026-01-20 | 2026-03-25 | 64 | 237 | 7 | TCL GA was pending | Fully Completed |  | Released
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA623037554260 | TCS (PASSPORT SEVA PROJECT) | Installation - Customer | 2026-01-13 | 2026-01-20 |  | -46042 | 237 | 7 | TCL GA was pending | WIP |  | Released
East | Orissa | RF Capacity augmentation 65 BS 100 to 45 | BTS | BTS | OR3007 | GHASISAHI-1 | Dismantle - BS(PMP) | 2026-02-06 | 2026-02-07 | 2026-02-13 | 6 | 219 | 7 |  | Dismantle completed | Details shared | Released
East | Orissa | RF Capacity augmentation 65 BS 100 to 45 | BTS | BTS | ORIKHU0541 | BBSR_GSM_17 | Dismantle - BS(PMP) | 2026-02-08 | 2026-02-08 | 2026-02-23 | 15 | 218 | 7 |  | Dismantle completed | Details shared | Released
East | Orissa | RF Capacity augmentation 65 BS 100 to 45 | UBR | BTS | ORIKHU0541 | BBSR_GSM_17 | Dismantle - UBR BH | 2026-02-08 | 2026-02-08 | 2026-02-23 | 15 | 218 | 7 |  | Dismantle completed | Details shared | Released
East | Orissa | PtP To PmP Conversion-5 | Customer | Customer | 091BHUB623029415318 | ATC Telecom Infrastructure Private Limited | Dismantle - Customer | 2026-03-09 | 2026-03-09 | 2026-04-15 | 37 | 189 | 7 |  | Dismantle completed |  | Released
East | Orissa | PtP To PmP Conversion-5 | Customer | Customer | 091BHUB623031266711 | Maruti Suzuki India Ltd | Dismantle - Customer | 2026-03-09 | 2026-03-09 | 2026-04-15 | 37 | 189 | 7 |  | Dismantle completed |  | Released
East | West Bengal | PtP To PmP Conversion-5 | Customer | Customer | 091BURD623013072306 | INDIAN BANK (Erstwhile Allahabad Bank) | Dismantle - Customer | 2026-03-09 | 2026-03-09 |  |  | 189 | 7 |  | Pending/YTS |  | Released
East | Orissa | Non Performing BS Optimization Ph-11 | UBR | UBR | ORIPUR0330 | Station Road (puri district) | UBR BH survey | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2 | 175 | 2 |  | Survey Completed | Report shared | Released
East | Orissa | Non Performing BS Optimization Ph-11 | UBR | UBR | ORIPUR0330 | Station Road (puri district) | Installation - UBR BH | 2026-03-31 | 2026-05-03 | 2026-05-06 | 3 | 134 | 7 |  | Fully Completed |  | Released
East | Orissa | T34P-Switch replacement FY25 | Switch | BTS | INOD000162 | KAPALESWAR | Installation - Switch | 2026-04-01 | 2026-04-01 | 2026-04-02 | 1 | 166 | 7 |  | Fully Completed |  | Released | WCC pending
East | Orissa | T34P-Switch replacement FY25 | Switch | BTS | INOD000162 | KAPALESWAR | Migration - Switch | 2026-04-01 | 2026-04-02 | 2026-04-05 | 3 | 165 |  | As per DT | Migrated |  | Released | WCC pending
East | Orissa | Non Performing BS Optimization Ph-11 | UBR | BTS | ORIPUR0330 | Station Road (puri district) | UBR PE | 2026-05-09 | 2026-05-09 | 2026-05-10 | 1 | 128 | 1 | As per DT | Migrated |  | Released
East | Jharkhand | CX4 BH Con. BH Migr 17 BS FY26 | BTS | BTS | JHAEAS0133 | Chandil_01 | Migration | 2026-05-07 | 2026-05-07 | 2026-05-14 | 7 | 130 |  | As per DT | Migrated |  | Released
East | Orissa | CX4 to conventional backhaul PH 3 | UBR | UBR | TROR0037 | R.k Colony nabarangapur | UBR BH survey | 2026-06-04 | 2026-06-05 | 2026-06-19 | 14 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Orissa | ZTS Relocation FY26 Ph-2 | UBR + Relocation | BTS | OR/KE/VO/0362 | Kendrapara | UBR BH survey | 2026-06-04 | 2026-06-05 | 2026-06-13 | 8 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Orissa | ZTS Relocation FY26 Ph-2 | UBR + Relocation | BTS | OR/KE/VO/0362 | Kendrapara | Survey - BS(PMP) | 2026-06-04 | 2026-06-05 | 2026-06-13 | 8 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Orissa | ZTS Relocation FY26 Ph-2 | UBR + Relocation | Customer | 3331248740 | INDIAN OVERSEAS BANK | Survey - Customer | 2026-06-04 | 2026-06-05 | 2026-06-18 | 13 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Orissa | ZTS Relocation FY26 Ph-2 | UBR + Relocation | Customer | 091KEND6230A0219048 | Directorate of Income Tax (Systems) | Survey - Customer | 2026-06-04 | 2026-06-05 | 2026-06-18 | 13 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Orissa | ZTS Relocation FY26 Ph-2 | UBR + Relocation | Customer | 091KEND6230A0337934 | PNB METLIFE INDIA INSURANCE COMPANY LIMITED | Survey - Customer | 2026-06-04 | 2026-06-05 | 2026-06-18 | 13 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Orissa | ZTS Relocation FY26 Ph-2 | UBR + Relocation | Customer | 091KEND623037541612 | TCS PASSPORT SEVA PROJECT | Survey - Customer | 2026-06-04 | 2026-06-05 | 2026-06-18 | 13 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Orissa | ZTS Relocation FY26 Ph-2 | UBR + Relocation | Customer | 091CUTT623036817532 | Central Bank of India | Survey - Customer | 2026-06-04 | 2026-06-05 | 2026-06-18 | 13 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Orissa | ZTS Relocation FY26 Ph-2 | UBR + Relocation | Customer | 091KEND623034584731 | ICICI Bank Limited | Survey - Customer | 2026-06-04 | 2026-06-05 | 2026-06-18 | 13 | 101 | 7 |  | Survey Completed | Report shared | Released | WCC pending
East | Sikkim | Low Potential BS & Sector Dismantling 70 | BTS | BTS | SKMEAS0005 | Gangtok_004(MG Marg) | Sector Dismantling | 2026-06-25 | 2026-06-26 | 2026-06-29 | 3 | 80 | 7 |  | Dismantle completed | Details shared | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091CUTT623036705696 | Axis Bank Limited | Survey - Customer | 2026-06-25 | 2026-07-06 | 2026-07-07 | 1 | 70 | 7 |  | Survey Completed | PMP Feasible with existing 3 mtr pole | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091CUTT6230A0006748 | FIS Payment Solutions & Services India Private Limited | Survey - Customer | 2026-06-25 | 2026-07-06 | 2026-07-07 | 1 | 70 | 7 |  | Survey Completed | PMP Feasible with existing 3 mtr pole | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091JAJP6230Z0000011 | Bharti AXA Life Insurance Company Limited | Survey - Customer | 2026-06-25 | 2026-07-01 |  |  | 75 | 7 |  | Pending/YTS |  | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091KORA623009931945 | IDBI Bank Limited | Survey - Customer | 2026-06-25 | [6 empty] | Pending/YTS |  | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091NAYA623008983704 | Bajaj Allianz Life Insurance Company Limited | Survey - Customer | 2026-06-25 | [6 empty] | Pending/YTS |  | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091KHOR623037777207 | HDFC BANK LIMITED | Survey - Customer | 2026-06-25 | 2026-07-06 | 2026-07-08 | 2 | 70 | 7 |  | Survey Completed | PMP not feasible for BTS not wihin 4 km | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091BHUB0300A0007214 | MATRIMONY.COM Limited | Survey - Customer | 2026-06-25 | 2026-07-05 | 2026-07-06 | 1 | 71 | 7 |  | Survey Completed | PMP Feasible with existing 3 mtr pole | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091ROUR623037541836 | TCS (PASSPORT SEVA PROJECT) | Survey - Customer | 2026-06-25 | 2026-07-06 | 2026-07-09 | 3 | 70 | 7 |  | Survey Completed | PMP Feasible with existing 24 mtr GBT mast | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091NAYA6230A0208174 | Tata AIA Life Insurance Company Limited | Survey - Customer | 2026-06-25 | [6 empty] | Pending/YTS |  | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091SILI623036824531 | Tata Motors Limited | Survey - Customer | 2026-06-25 | 2026-07-11 | 2026-07-13 | 2 | 65 | 7 |  | Survey Completed | PMP Feasible with 6 mtr existing pole | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091BEHA623012669181 | West Bengal state Electricity Distribution Company Ltd | Survey - Customer | 2026-06-25 | [6 empty] | Pending/YTS |  | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091JALP6230A0053842 | Tata AIA Life Insurance Company Limited | Survey - Customer | 2026-06-25 | 2026-07-20 | 2026-07-21 | 1 | 56 | 7 |  | Survey Completed | PMP Feasible with existing 3 mtr pole | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091SILI623031713486 | Maruti Suzuki India Limited | Survey - Customer | 2026-06-25 | 2026-07-06 | 2026-07-08 | 2 | 70 | 7 |  | Survey Completed | PMP Feasible with existing 3 mtr pole | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091SILI0300A0019868 | LUPIN LIMITED | Survey - Customer | 2026-06-25 | 2026-07-06 | 2026-07-08 | 2 | 70 | 7 |  | Survey Completed | PMP Feasible with existing 3 mtr pole | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091KOLK0300A0133134 | HDFC Bank Limited | Survey - Customer | 2026-06-25 | 2026-07-01 | 2026-07-14 | 13 | 75 | 7 |  | Survey Completed | PMP Not feasible | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091JALP623037679662 | Bajaj Finance Limited | Survey - Customer | 2026-06-25 | 2026-07-01 | 2026-07-03 | 2 | 75 | 7 |  | Survey Completed | PMP Feasible with existing 3 mtr pole | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091ALIP623037546128 | TCS (PASSPORT SEVA PROJECT) | Survey - Customer | 2026-06-25 | [6 empty] | Pending/YTS |  | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091COOC623036787301 | Tata AIA Life Insurance Company Limited | Survey - Customer | 2026-06-25 | [6 empty] | Pending/YTS |  | Pending | WO pending
East | Orissa | P2P to PMP Phase 6 | Customer | Customer | 091BHUB0300A0007214 | MATRIMONY.COM Limited | Installation - Customer | 2026-07-26 | 2026-07-26 | 2026-07-27 | 1 | 50 | 7 |  | I&C Complete | Stability mail shared | Pending | WO pending
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA6230A0296946 | Directorate of Income Tax Systems | Migration - Customer | 2026-07-30 | 2026-07-30 | 2026-07-31 | 1 | 46 | 2 |  | Migrated |  | Released | WCC pending
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA623017007536 | UNION BANK OF INDIA | Migration - Customer | 2026-07-30 | 2026-07-30 | 2026-07-31 | 1 | 46 | 2 |  | Migrated |  | Released | WCC pending
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA0300A0312332 | SHRIRAM FINANCE LIMITED | Migration - Customer | 2026-07-30 | 2026-07-30 | 2026-07-31 | 1 | 46 | 2 |  | Migrated |  | Released | WCC pending
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA623038521612 | Tata AIA Life Insurance Company Limited | Migration - Customer | 2026-07-30 | 2026-07-30 | 2026-07-31 | 1 | 46 | 2 |  | Migrated |  | Released | WCC pending
East | Bihar | Radwin 5K Migration - PH-1 | Customer | Customer | 091AURA623037554260 | TCS (PASSPORT SEVA PROJECT) | Migration - Customer | 2026-07-30 | 2026-07-30 |  |  | 46 | 2 |  | Pending/YTS |  | Pending | WO pending
East | Sikkim | CX4 to conventional backhaul PH 3 | UBR | BTS | SKMEAS0005 | Gangtok_004(MG Marg) | UBR BH survey | 2026-07-30 | 2026-07-31 |  |  |  | 7 |  | Pending/YTS |  | Pending | WO pending
East | West Bengal | CX4 to conventional backhaul PH 3 | UBR | BTS | WEBSIK0759 | Kalingpong_001 | UBR BH survey | 2026-07-30 | 2026-07-31 |  |  |  | 7 |  | Pending/YTS |  | Pending | WO pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | BTS | WEBQKG0670 | Medinipur (M) 2 | BS+UBR LOS Survey | 2026-08-03 | 2026-08-10 | 2026-09-01 | 22 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | UBR | WEBWES0970 | Midnapur_001 (Chandinibazar) | UBR LOS Survey | 2026-08-03 | 2026-08-10 | 2026-09-01 | 22 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN623037068891 | PUNJAB NATIONAL BANK | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-07 | 28 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN0300A0139627 | ADITYA BIRLA SUN LIFE INSURANCE COMPANY LIMITED | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-07 | 28 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN6230A0231440 | HDFC LIFE INSURANCE COMPANY LIMITED | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-02 | 23 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN623034728667 | UNION BANK OF INDIA- erstwhile CB | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-02 | 23 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN623012666915 | West Bengal state Electricity Distribution Company Ltd | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-02 | 23 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN030037129170 | Jubilant Foodworks Limited | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-02 | 23 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN0300A0349342 | DR. LAL PATHLABS Limited | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-07 | 28 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN623013065113 | West Bengal state Electricity Distribution Company Ltd | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-07 | 28 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | High Colo Opex BTS & ZTS relocation | Relocation + UBR | Customer | 091MIDN623037049104 | HDFC BANK LIMITED | Survey - Customer | 2026-08-03 | 2026-08-10 | 2026-09-02 | 23 | 35 | 7 |  | Survey Completed |  | Released | WCC pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091SILI623031713486 | Maruti Suzuki India Limited | Installation - Customer | 2026-08-31 | 2026-08-31 | 2026-09-01 | 1 | 14 | 7 |  | I&C Complete |  | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091SILI0300A0019868 | LUPIN LIMITED | Installation - Customer | 2026-08-31 | 2026-08-31 | 2026-09-01 | 1 | 14 | 7 |  | I&C Complete |  | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091SILI623031713486 | Maruti Suzuki India Limited | Migration - Customer | 2026-09-01 | 2026-09-01 | 2026-09-02 | 1 | 13 | 2 |  | Migrated |  | Pending | WO pending
East | West Bengal | P2P to PMP Phase 6 | Customer | Customer | 091SILI0300A0019868 | LUPIN LIMITED | Migration - Customer | 2026-09-01 | 2026-09-01 | 2026-09-02 | 1 | 13 | 2 |  | Migrated |  | Pending | WO pending
East | Orissa | L1-L2 improvement FY24 Ph-2, 80 sites | BTS | BTS | ORIKHU0268 | Niladri Vihar | Installation - Switch | 2026-08-21 | 2026-08-31 | 2026-09-01 | 1 | 14 | 7 |  | I&C Complete |  | Pending | WO pending
East | Orissa | L1-L2 improvement FY24 Ph-2, 80 sites | BTS | BTS | ORIKHU0268 | Niladri Vihar | Migration - Switch | 2026-09-01 | 2026-09-01 | 2026-09-06 | 5 | 13 | 2 |  | Migrated |  | Pending | WO pending
East | Orissa | L1-L2 improvement FY24 Ph-2, 80 sites | BTS | BTS | IN-2035228 | BALUGAON | Installation - Switch | 2026-08-21 | 2026-09-04 |  |  | 10 | 7 |  | Pending/YTS |  | Pending | WO pending
Formulas:
Aging = TODAY()-[Permission Recieved Date]

## Team details
Sl.No | Region / Zone | Vendor Name | Name of FE/Tech (SD only) | DOB | Mobile Number | Emergency Response Contact Name | Emergency Response Contact Number | Qualification | Medical Certificate No. | Medical Certificate Issue Date | Email ID | EMP ID | Date of Joining | Major location | City Name | Work at Height (CBTHR/FARM Tocli) Certification Status (Y/N) | W@H Certificate number | Month & Year of Safety Training | Month & Year of Expiry | Transport Mode(2W/4W/Public Transport) | 2 Wheeler Driving License Availability (Yes/No) | 2W DDT Training Status(Completed/Pending) | 2W DDT Training Date | 2W DDT Expiry Date | H&S Induction Training Status (Completed/Pending) | H&S Induction training date | Experience (In ) | Epassport Availability | Epassport Status as per Portal | Epassport Expiry date | Epassport ID-SD | EPTW Mapped Status(Y/N) | EPTW User name
1 | East | Malfonic Network Communication Pvt Ltd | Jayanta Kumar Sahoo | 1998-07-02 | 7327946989 | Prafulla Sahoo | 8144198804 | Graduation | SM-MED- 15684 | 2023-05-22 | jayantasahoo3843@gmail.com | 01-19092022 | 19-09-22 | Orissa | Bhubaneswar | Y | 25260003 | 2025-04-02 | 2027-04-01 | Public Transport | No | NA | NA | NA | Completed | 2022-12-16 | 1 Yr | Yes | Active | 2027-04-01 | TCL/SD/SD/JAN/2500512 | Y | jayantasahoo3843
2 | East | Malfonic Network Communication Pvt Ltd | Kishor Sarkar | 1986-09-12 | 9924896809 | Riya Sarkar | 9832762246 | Graduation | SM-MED-17303 | 2023-07-25 | kishorsarkar2012@gmail.com | 01-20210414 | 14-04-21 | West Bengal | Kolkata | Y | 25260401 | 2025-09-15 | 2027-09-15 | Public Transport | No | NA | NA | NA | Completed | 2023-08-11 | 3 Yrs | Yes | Active | 2027-09-15 | TCL/SD/SD/JAN/2500525 | Y | 21177
3 | East | Malfonic Network Communication Pvt Ltd | Linkan Sharma | 2003-08-04 | 8515933473 | Litan Sharma | 7548960041 | 12th | SM-MED-21715 | 2024-08-03 | linkansharma003@gmail.com | 02-03062024 | 2025-05-06 | West Bengal | Kolkata | Y | 24250116 | 2024-08-04 | 2026-08-04 | Public Transport | No | NA | NA | NA | Completed | 2025-08-05 | 1 Yr | Yes | Active | 2026-08-03 | TCL/SD/SD/MAR/2502825 | Y | linkansharma003
4 | East | Malfonic Network Communication Pvt Ltd | Joy Mohabta | 2024-10-15 | 9832578982 | Smritimay Jana | 9830210541 | 10th | SM-MED-260105 | 2026-01-15 | mohantan707@gmail.com | 01-19122025 | 2025-01-11 | West Bengal | Siliguri | Y | 25260617 | 2026-01-22 | 2028-01-22 | Public Transport | No | NA | NA | NA | Completed | 2025-11-15 | 1 Yr | Yes | Active | NO | NO | Y | NA
5 | East | Malfonic Network Communication Pvt Ltd | Subha Barman | [10 empty] | West Bengal | Siliguri | Y | 25260699 | 2026-02-16 | 2028-02-15 | Public Transport | No | NA | NA | NA | Completed | 2026-06-05 | 0.5 Yrs | Yes | Active | 2028-02-15 | TCL/WOPI/WI/JUN/2605846 | Y | 2605846
6 | East | Malfonic Network Communication Pvt Ltd | Samir Bala | [10 empty] | Orissa | Bhubaneswar | Y | 24250288 | 2024-11-17 | 2026-11-16 | Public Transport | No | NA | NA | NA
7 | East | Malfonic Network Communication Pvt Ltd | Balai Malakar | [10 empty] | Orissa | Bhubaneswar | Y | 25260603 | 2026-06-19 | 2028-06-18 | Public Transport | No | NA | NA | NA