## DATA
Site ID | Site Name | Site Scope | Activity receive date | Material Received /Permission Availability | Activity Done Date | Status | Agging | TAT | Remarks 1 | Work order no | Work Order NUmber
ORIQCU0115 | Gunjarpur | Sector dismantle | 2025-06-09 |  | 2025-06-10 | Fully Completed | 462 | 1 |  |  | 25-26/Oct-498, 25-26/Oct-499
ORIKEO0239 | Joda | Sector dismantle | 2025-06-09 |  | 2025-06-11 | Fully Completed | 462 | 2 |  |  | 25-26/Nov-107,25-26/Nov-108,25-26/Oct-497
091KEND623009594833 | The Federal Bank Limited | CPE Installation | 2025-06-16 |  | 2025-06-18 | Fully Completed | 455 | 2 |  |  | 25-26/Jul-383
091KEND623016813242 | UNION BANK OF INDIA | CPE Installation | 2025-06-16 |  | 2025-06-18 | Fully Completed | 455 | 2 |  |  | 25-26/Jul-384
091KEND623037771487 | IDBI BANK LTD | CPE Installation | 2025-06-16 |  | 2025-06-19 | Fully Completed | 455 | 3 |  |  | 25-26/Jul-385
2155 | Bhawanipatna 1 (jagganath temple road) | BTS Installation | 2025-06-09 |  | 2025-06-27 | Fully Completed | 462 | 18 |  |  | 25-26/Jul-388
2155 | Bhawanipatna 1 (jagganath temple road) | AT Activity | 2025-06-27 |  | 2025-06-28 | Fully Completed | 444 | 1 |  |  | 25-26/Jul-387
ORIKEN0223 | Pattamundai_IM | PE Activity | 2025-06-26 |  | 2025-06-29 | Fully Completed | 445 | 3 |  |  | 25-26/Jul-389
ORIJAG0396 | PPL Colony | BTS Survey | 2025-06-26 |  | 2025-07-02 | Fully Completed | 445 | 6 |  |  | 25-26/Jul-075
ORIBAR0053 | Maharaja | BTS Survey | 2025-06-26 |  | 2025-07-07 | Fully Completed | 445 | 11 |  |  | 25-26/Jul-074
ORIKEO0239 | Joda | Sector dismantle | 2025-06-09 |  | 2025-06-11 | Fully Completed | 462 | 2 |  |  | 25-26/Oct-496
706659 | Hinjilikatu (Bhapur)_GSM_R | BTS survey & UBR BH survey | 2025-07-16 |  | 2025-07-22 | Fully Completed | 425 | 6 | Survey completed but There was some issue with getting permission at the BTS, so I couldn't take proper snaps |  | 25-26/Aug-390, 25-26/Sep-406
3331247967 | Bajaj Allianz Life Insurance Co Ltd | CPE Installation | 2025-07-22 |  | 2025-07-24 | Fully Completed | 419 | 2 |  |  | 25-26/Aug-392
091KALA030038625399 | HDB Financial Services Limited | CPE Installation | 2025-07-23 |  | 2025-07-28 | Fully Completed | 418 | 5 |  |  | 25-26/Jul-706
091KALA623037541964 | TCS PASSPORT SEVA PROJECT | CPE Installation | 2025-07-23 |  | 2025-07-28 | Fully Completed | 418 | 5 |  |  | 25-26/Jul-707
091KALA623034702152 | UNION BANK OF INDIA- erstwhile CB | CPE Installation | 2025-07-23 |  | 2025-08-07 | Fully Completed | 418 | 15 |  |  | 25-26/Jul-708
091KALA6230A0219097 | Directorate of Income Tax (Systems) | CPE Installation | 2025-07-23 |  | 2025-09-25 | WIP, Fully Completed | 418 | 64 |  |  | 25-26/Jul-709
ORIJAG0396 _to ORICUT0562 | PPL Colony_ to PAR_GSM_01 | UBR BH installation | 2025-07-30 |  | 2025-08-03 | Fully Completed | 411 | 4 | physical installation has been completed |  | 25-26/Aug-161
ORIBAR0053_to ORIBAR1160 | Maharaja_OR01530_Nagenpalli Bargarh | UBR BH installation | 2025-07-30 |  |  | HOLD BY TCL | 411 | -45868 |  |  | pending
3331247967 | Bajaj Allianz Life Insurance Co Ltd | CPE Migraction | 2025-08-04 |  | 2025-08-05 | Fully Completed | 406 | 1 | Migraction completed |  | 25-26/Aug-393
3331247967 | Bajaj Allianz Life Insurance Co Ltd | CPE Recovery | 2025-08-05 |  | 2025-08-05 | Fully Completed | 405 | 0 | CPE Recovery completed |  | 25-26/Sep-403
091KEND623016813242 | UNION BANK OF INDIA | CPE Recovery | 2025-08-05 |  | 2025-08-05 | Fully Completed | 405 | 0 | CPE Recovery completed |  | 25-26/Sep-404
091KEND623037771487 | IDBI BANK LTD | CPE Recovery | 2025-08-05 |  | 2025-08-05 | Fully Completed | 405 | 0 | CPE Recovery completed |  | 25-26/Sep-405
ORIKEN0223 | Pattamundai_IM | Conventor Recovery | 2025-08-05 |  | 2025-08-05 | Fully Completed | 405 | 0 | Conventor Recovery |  | 25-26/Nov-612
091KALA623037541964 | TCS PASSPORT SEVA PROJECT | CPE Migraction | 2205-08-18 |  | 2205-08-18 | Fully Completed | -65351 | 0 | CPE Migracton completed |  | 25-26/Jul-711
091KALA030038625399 | HDB Financial Services Limited | CPE Migraction | 2205-08-18 |  | 2205-08-18 | Fully Completed | -65351 | 0 | CPE Migracton completed |  | 25-26/Jul-710
091KALA6230A0219097 | Directorate of Income Tax (Systems) | CPE Migraction | 2025-09-25 |  | 2025-09-25 | Fully Completed | 354 | 0 | CPE Migracton completed |  | 25-26/Jul-713
091KEND623016813242 | UNION BANK OF INDIA | CPE Migraction | 2025-10-06 |  | 2025-10-06 | Fully Completed | 343 | 0 | CPE Migracton completed |  | 25-26/Jul-702
091MIDN623012668165 | West Bengal state Electricity Distribution Company Ltd | CPE Survey | 2025-10-10 |  |  | WIP | 339 | -45940 | Permission Issue |  | 25-26/Jan-238
091KOLK6230A0072630 | SBICAP Securities Limited | CPE Survey | 2025-10-10 |  | 2025-11-03 | Fully Completed | 339 | 24 |  |  | 25-26/Nov-382
091HOWR623015015451 | TATA STEEL LIMITED | CPE Survey | 2025-10-10 |  |  | Fully Completed | 339 | -45940 |  |  | 25-26/Nov-370
091KOLK623035688319 | JANA SMALL FINANCE BANK LIMITED. | CPE Survey | 2025-10-10 |  |  | Fully Completed | 339 | -45940 |  |  | 25-26/Nov-373
091DOMJ6230A0004637 | 3M India Limited | CPE Survey | 2025-10-10 |  | 2026-10-11 | Fully Completed | 339 | 366 |  |  | 25-26/Nov-376
ORIGAN1061 | Hinjilikatu(Bhapur)_GSM | UBR BH installation | 2025-10-15 |  |  | WIP | 334 | -45945 | Permission issue |  | 25-26/Nov-712
ORIGAN1061 | Hinjilikatu(Bhapur)_GSM | BTS Installation | 2025-10-15 |  |  | WIP | 334 | -45945 | Permission issue |  | 25-26/Nov-713
091MIDN623012667267 | West Bengal state Electricity Distribution Company Ltd | CPE Survey | 2025-12-05 |  | 2025-12-08 | Fully Completed | 283 | 3 |  |  | 25-26/Jan-239
091MIDN623012667299 | West Bengal state Electricity Distribution Company Ltd | CPE Survey | 2025-12-05 |  | 2025-12-08 | Fully Completed | 283 | 3 |  |  | 25-26/Jan-240
091MURS623005582079 | TCS (PASSPORT SEVA PROJECT) | CPE Survey | 2025-12-05 |  |  |  | 283 | -45996 | Permission issue |  | pending
091KALA6230A0288245 | Murugappa Management Services Limited | CPE Installation | 2026-01-05 |  | 2026-01-08 | Fully Completed | 252 | 3 |  |  | 25-26/Jan-242
091KOHI623037611875 | Indian Bank |  | 2026-01-14 |  |  |  | 243 | -46036 |  |  | 25-26/Feb-059
091KARI623037547113 | TCS PASSPORT SEVA PROJECT | CPE Survey | 2026-01-14 |  | 2026-01-21 | Fully Completed | 243 | 7 |  |  | 25-26/Feb-058
091KALA6230A0288245 | Murugappa Management Services Limited | CPE Installation | 2026-01-05 |  | 2026-01-08 | Fully Completed | 252 | 3 |  |  | 25-26/Jan-242
ORIKOR0286 | Jeypur_02 | BH Survey | 2026-01-27 |  | 2026-01-30 | Fully Completed | 230 | 3 |  |  | 25-26/Feb-252
TROR0035 | Jeypur | BH Survey | 2026-01-27 |  | 2026-01-30 | Fully Completed | 230 | 3 | Activity Not Complete And Given One Visit |  | 25-26/Feb-251
SKMEAS0005 | Gangtok_004(MG Marg) | Sector installation | 2026-02-05 |  |  | Permission Issue | 221 | -46058 | Permission issue |  | 25-26/Feb-071
IN-2008521 | SDAR HAZARIBAG | BTS Survey | 2026-02-05 |  | 2026-02-11 | Fully Completed | 221 | 6 |  |  | 25-26/Feb-255
JHAHAZ0392 | BIH_Hazaribag_011 | BTS Survey | 2026-02-07 |  | 2026-02-11 | Fully Completed | 219 | 4 |  |  | 25-26/Feb-256
BH6018-JHARAN0224 | Namkum/Khijri | BTS Survey | 2026-02-07 |  | 2026-02-12 | Fully Completed | 219 | 5 | Bts Survey Completed |  | 25-26/Feb-257
JHARAN0224 | Namkum | BTS Survey | 2026-02-07 |  | 2026-02-12 | Fully Completed | 219 | 5 |  |  | 25-26/Feb-257
BIHQBG0152/BIGT14418 | Babutola/BIGT14418 | BTS Survey | 2026-02-05 |  | 2026-02-13 | Fully Completed | 221 | 8 | bts Survey Completed |  | 25-26/Feb-253
VFJHGOD0158 | Rotara Chowk | UBR BH Survey | 2026-02-05 |  | 2026-02-13 | Fully Completed | 221 | 8 | BH Survey Completed |  | 25-26/Feb-254
091BANK623016988262 | UNION BANK OF INDIA | Los survey | 2026-02-13 |  | 2026-02-14 | Fully Completed | 213 | 1 |  |  | 25-26/Feb-354
091BANK6230A0082583 | SBI Life Insurance Company Limited | Los survey | 2026-02-13 |  | 2026-02-14 | Fully Completed | 213 | 1 |  |  | 25-26/Feb-355
091BANK623037548300 | TCS PASSPORT SEVA PROJECT | Los survey | 2026-02-13 |  | 2026-02-14 | Fully Completed | 213 | 1 |  |  | 25-26/Feb-356
091BANK6230A0378261 | BAJAJ LIFE INSURANCE LIMITED | Los survey | 2026-02-13 |  | 2026-02-14 | Fully Completed | 213 | 1 |  |  | 25-26/Feb-357
ORIKAL0211 | Bhawanipatna_2 | BTS Dismintal | 2026-02-07 |  | 2026-02-21 | Fully Completed | 219 | 14 |  |  | 25-26/Feb-144
091HAZA623035451264 | HDFC Bank Limited | LOS survey | 2026-02-25 |  | 2026-03-02 | Fully Completed | 201 | 5 |  |  | 25-26/Feb-367
091HAZA623036194122 | Bank of India | LOS survey | 2026-02-25 |  | 2026-03-02 | Fully Completed | 201 | 5 |  |  | 25-26/Feb-368
091HAZA0300A0194599 | ICICI Lombard General Insurance Company Limited | LOS survey | 2026-02-25 |  | 2026-03-02 | Fully Completed | 201 | 5 |  |  | 25-26/Feb-369
091HAZA6230A0213204 | Tata AIA Life Insurance Company Limited | LOS survey | 2026-02-25 |  | 2026-03-02 | Fully Completed | 201 | 5 |  |  | 25-26/Feb-370
091HAZA6230A0140778 | ICICI Prudential Asset Management Company Limited | LOS survey | 2026-02-25 |  | 2026-03-02 | Fully Completed | 201 | 5 |  |  | 25-26/Feb-371
VFJHGOD0158- JHAGOD0282 | Rotara Chowk - Godda_1 | UBR BH Installation | 2026-03-05 |  | 2026-03-22 | Fully Completed | 193 | 17 | Material Not available / Material recv- 13 evng by hand pickup / 19th reachability done /22nd - PE completed |  | 25-26/Mar-268
091KOLK623035688319 | JANA SMALL FINANCE BANK LIMITED. | Dismantle | 2026-03-06 |  | 2026-03-07 | Fully Completed | 192 | 1 |  |  | 25-26/Mar-068
091BHUB6230A0188101 | JM Financial Services Limited | P2P Installation | 2026-03-23 |  |  | Physical Completed | 175 | -46104 | Material recevied/ 24 evng |  | 25-26/Mar-419
ORIKOR0286-OR/KO/VO/0324 | Jeypur_02-Umuri | UBR BH Installation+ Switch Installation | 2026-03-25 |  |  | Fully Completed | 173 | -46106 | Material recevied |  | 26-27/Apr-017 And 26-27/Apr-018
BIGT14418 |  | Sector Installation | 2026-03-26 | Material received- 03-04-26 | 18-04-2026 | Physical Completed, PP Closure WIP, Report WIP | 172 | #VALUE! | material received- 03-04026
JHARAN0224 | Namkum | Sector installation +Switch insttaion | 2026-03-19 | (Material 25-03-26) - (31-03-26 - permisison availbale) | 2026-04-02 | Report WIP | 179 | 14 | (Material received -25-03-26 ), (31-03-26 permisison available) ,(Physical completed -02-04-26) |  | 26-27/Apr-296 / 26-27/Apr-299
JHAHAZ0495 -JHAHAZ0165 | Millat Colony Hazaribagh - Hazaribagh Nawabganj | UBR BH Installation | 2026-04-06 | Material Recevied |  | Fully Completed | 161 | -46118 | All Materal Reacved But Redwin BackHall Not Received |  | 26-27/Apr-294 / 26-27/Apr-296
JHAHAZ0495 - JHAHAZ0392 | Millat Colony Hazaribagh -BIH_Hazaribag_011 | UBR BH Installation | 2026-04-06 | Material Recevied |  | Fully Completed | 161 | -46118 |  |  | 26-27/Apr-293
JHAHAZ0495 | Millat Colony Hazaribagh | Sector installation +Switch Installation | 2026-04-06 | Material Recevied |  | Physical Completed | 161 | -46118 |  |  | 26-27/Apr-295
091BHUB623007581658 | Venkateshwara Hatcheries Private Limited |  | 2026-04-15 | Material Recevied |  | Fully Completed | 152 | -46127 |  |  | 26-27/Apr-075 And 26-27/Apr-076
091BISH623035499618 | FIS Payment Solutions & Services India Pvt. Ltd | WAN Aggregator Installation | 2026-04-10 | Maetrial Recevied | 2026-04-13 | Fully Completed | 157 | 3 |  |  | 26-27/Apr-073 And 26-27/Apr-074
IN-2000091 | ASRT10091 | UBR BH Survey | 2026-06-04 | NA | 2026-06-07 | Fully Completed | 102 | 3
INOD000171 | CHIKATA MATI | UBR BH Survey | 2026-06-04 | NA | 2026-06-11 | Fully Completed | 102 | 7
IN-1068107 | BALURGHAT-5 | UBR BH Survey | 2026-06-04 | NA | 2026-06-05 | Fully Completed | 102 | 1
IN-1064570 | ESILSILIGURI201 | BTS Survey | 2026-06-04 | NA | 2026-06-06 | Fully Completed | 102 | 2
WEBDAR0102 | UBR_Siliguri_004 (Hakimpara) | UBR BH Survey | 2026-06-04 | NA | 2026-06-06 | Fully Completed | 102 | 2
091DARJ623016826997 | UNION BANK OF INDIA- erstwhile AB | LOS Survey | 2026-06-09 |  | 2026-06-11 | Fully Completed | 97 | 2
091DARJ623009375511 | INDIAN OVERSEAS BANK | LOS Survey | 2026-06-09 |  | 2026-06-11 | Fully Completed | 97 | 2
091SILI623012664846 | West Bengal state Electricity Distribution Company Ltd | LOS Survey | 2026-06-09 |  | 2026-06-11 | Fully Completed | 97 | 2
091SILI623032017621 | UNION BANK OF INDIA | LOS Survey | 2026-06-09 |  | 2026-06-11 | Fully Completed | 97 | 2
091SILI623012668861 | West Bengal state Electricity Distribution Company Ltd | LOS Survey | 2026-06-09 |  | 2026-06-11 | Fully Completed | 97 | 2
091DARJ0300A0268079 | Jubilant Foodworks Limited | LOS Survey | 2026-06-09 |  | 2026-06-11 | Fully Completed | 97 | 2
091SILI623014558051 | HDFC Bank Limited | LOS Survey | 2026-06-09 |  | 2026-06-11 | Fully Completed | 97 | 2
IN-1038179 | METRO PLAZA | BTS Survey | 2026-06-09 |  | 2026-06-12 | Fully Completed | 97 | 3
TCLNLDPOP_Siliguri | Merchant Square | UBR BH Survey | 2026-06-09 |  | 2026-06-13 | Fully Completed | 97 | 4
WEBDAR0105 | MATIGARA | UBR BH Survey | 2026-06-09 |  | 2026-06-13 | Fully Completed | 97 | 4
091BANK623037548300 | TCS PASSPORT SEVA PROJECT | installation | 2026-06-05 |  | 2026-06-12 | Fully Completed | 101 | 7
091BANK6230A0378261 | BAJAJ LIFE INSURANCE LIMITED | installation | 2026-06-05 |  | 2026-06-12 | Fully Completed | 101 | 7
091BANK6230A0082583 | SBI Life Insurance Company Limited | installation | 2026-06-05 |  |  | WIP | 101 | -46178
091BANK623016988262 | UNION BANK OF INDIA | installation | 2026-06-05 |  |  | WIP | 101 | -46178
091BHUB6230Z0000002 | Bharti AXA Life Insurance Company Limited | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091BOKA623037549314 | TCS (PASSPORT SEVA PROJECT) | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091KHOR623016165178 | IndusInd Bank Limited | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091CUTT623038266741 | Bank of India | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091CUTT623017954792 | Havells India Limited | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091SAMB6230A0091487 | Axis Bank Limited | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091ROUR623009555031 | HDFC LIFE INSURANCE COMPANY LIMITED | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091DHAN6230A0060178 | Bharti AXA Life Insurance Company Limited | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091HAZA623038270847 | Bank of India | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
091HAZA623016408125 | SBI FUNDS MANAGEMENT LIMITED | Survey | 2026-06-25 |  |  | WIP | 81 | -46198
Formulas:
Agging = TODAY()-[Activity receive date]

## Team Details
Team Name | Location | Team Type SA / Team Type WI | E-Passport status | Remarks
Gaurav kumar | Patna | WI/SD | Y | Added
Santosh Singh | Kolkata | WI/SD | Y
Shyamapada Panda | Kolkata | WI/SD | Y
Manoranjan kumar | Bhubaneswar | SA/WI/SD | Y
PRODUNYAGOGOI | GUWAHATI | SA | Y
SONU KUMAR RAJAK | Dhanbad | SA/WI | Y | Need to check
Jai Prakash Kumar | Rourkela | SA/WI | Y
SubhamUpadhyaya | Brahmapur | SA/WI | Y
UTKAL KESHARI SAHOO | Kendujhar | SA/WI | N | Need to check
Raj kumar | Patna | WI/SD | Y
Kush kumar gupta | Kolkata | WI/SD | Y
Arindam jit | Kolkata | SA | N | Need to check
Anjan Paul | BBSR | WI/SD | N | Under Porcess
Nipu Nayak | BBSR | WI/SD | Y
Sehnawaz | Hazaribag | SA/WI | Y
Sahil | Hazaribag | SA/WI | Y

## Sheet4
Team Name | Location | Team Type SA / Team Type WI | E-Passport status | Remarks | PTW NO
Gaurav kumar | Patna | WI/SD | Y
Raj kumar | Patna | WI/SD | Y
Santosh Singh | Kolkata | WI/SD | Y
Shyamapada Panda | Kolkata | WI/SD | Y
Kush kumar gupta | Kolkata | WI/SD | Y
Debasish Karmarkar | Kolkata | WI/SD/ SA | Y
Jai Prakash Kumar | Rourkela | SA/WI | Y | We have use only Rourkela & Sambalpur location
Satyabadi sahoo | Rourkela | SA/WI | WIP | We have use only Rourkela & Sambalpur location
AIJIT PEGU | Guwahati | WI/SD | Y
Bikom Rabh | Guwahati | WI/SD | Y